## Cover Page .
S | CASHFLOW FORECAST FOR PROPOSED HEAD OFFICE FOR PRIORITY INSURANCE
OCTOBER, 2026
|  | www.spektra.global // +233 30 321 7241 // | SPEKTRA GLOBAL LTD
GROUND TOTAL TO SUMMARY

## CASHFLOW SUMMARY
PROPOSED CASH FLOW AGGREGATED
PAYMENT NO. | MONTH, YEAR | AMOUNT (US$)
PMT 1 (ADV.)
PMT 2
PMT 3
PMT 4
PMT 5
PMT 6
PMT 7
PMT 8
PMT 9
TOTAL PAYMENT
PROPOSED CASH FLOW MONTHLY
PAYMENT NO. | MONTH, YEAR | AMOUNT (US$)
PMT 1 (ADV)
PMT 2
PMT 3
PMT 4
PMT 5
PMT 6
PMT 7
PMT 8
PMT 9
PMT 10
PMT 11
PMT 12
PMT 13
PMT 14
PMT 15
PMT 16
PMT 17
PMT 18
PMT 19
PMT 20
PMT 21
PMT 22
PMT 23
PMT 24
PMT 25
PMT 26
PMT 27
TOTAL PAYMENT

## CASHFLOW
ITEM | DESCRIPTION |  | TOTAL |  | TOTAL | START MONTH | DURATION (MONTHS)
0
A | ADVANCE MOBILIZATION
| Contract Signing | 100% |  |  |  | 0 | 1
B
| (100%) Site Possession and Hoarding | 30% |  |  |  | 1 | 1
| (100%) Site Setup and Mobilization | 20% |  |  |  | 2 | 1
| (100%) Site Maintenance | 50% |  |  |  | 3 | 22
C
| (0%) Start of Demolition Works | 80% |  |  |  | 1 | 1
| (100%) End of Demolition Works | 20% |  |  |  | 2 | 1
D
| Procurement Phase I (Substructure materials on site and in transit) (0%) | 50% |  |  |  | 1 | 2
| (50%) Completion of Ground Works | 25% |  |  |  | 3 | 1
| (100%) Completion of Substructure Concrete Works | 25% |  |  |  | 4 | 1
E
| (0%) Start of Sub-Basement Floor Structure | 30% |  |  |  | 3 | 3
| (100%) Completion of Structure | 20% |  |  |  | 6 | 1
| (0%) Start of Finishings and MEP | 30% |  |  |  | 7 | 10
| (100%) Completion of Finishings and MEP | 20% |  |  |  | 17 | 2
F
| (0%) Start of Ground Floor Structure | 30% |  |  |  | 5 | 2
| (100%) Completion of Structure | 20% |  |  |  | 7 | 1
| (0%) Start of Finishings and MEP | 30% |  |  |  | 8 | 11
| (100%) Completion of Finishings and MEP | 20% |  |  |  | 19 | 2
G
| (0%) Start of First Floor Structure | 30% |  |  |  | 7 | 2
| (100%) Completion of Structure | 20% |  |  |  | 9 | 1
| (0%) Start of Finishings and MEP | 30% |  |  |  | 10 | 10
| (100%) Completion of Finishings and MEP | 20% |  |  |  | 20 | 2
H
| (0%) Start of Second Floor Structure | 30% |  |  |  | 9 | 2
| (100%) Completion of Structure | 20% |  |  |  | 11 | 1
| (0%) Start of Finishings and MEP | 30% |  |  |  | 12 | 8
| (100%) Completion of Finishings and MEP | 20% |  |  |  | 20 | 2
J
| (0%) Start of Third Floor Structure | 30% |  |  |  | 11 | 2
| (100%) Completion of Structure | 20% |  |  |  | 13 | 1
| (0%) Start of Finishings and MEP | 30% |  |  |  | 14 | 7
| (100%) Completion of Finishings and MEP | 20% |  |  |  | 21 | 2
K
| (0%) Start of Fourth Floor Structure | 30% |  |  |  | 13 | 2
| (100%) Completion of Structure | 20% |  |  |  | 15 | 1
| (0%) Start of Finishings and MEP | 30% |  |  |  | 16 | 5
| (100%) Completion of Finishings and MEP | 20% |  |  |  | 21 | 2
L
| (0%) Start of Fifth Floor Structure | 30% |  |  |  | 15 | 2
| (100%) Completion of Structure | 20% |  |  |  | 17 | 1
| (0%) Start of Finishings and MEP | 30% |  |  |  | 18 | 3
| (100%) Completion of Finishings and MEP | 20% |  |  |  | 21 | 2
M
| (0%) Start of Kitchen Cabinetry/Wall Cladding works | 70% |  |  |  | 16 | 1
| 100% of works fabricated | 20% |  |  |  | 19 | 2
| 100% of works installed on site | 10% |  |  |  | 22 | 1
N
| First fix, sleeves and pipework | 60% |  |  |  | 4 | 15
| Second fix, testing and commissioning | 40% |  |  |  | 19 | 5
P
| First fix, conduits and containment | 60% |  |  |  | 4 | 15
| Second fix, testing and commissioning | 40% |  |  |  | 19 | 5
Q
| Procurement and fabrication of facade materials | 70% |  |  |  | 12 | 3
| Installation of facade | 30% |  |  |  | 15 | 8
R
| (50%) External works | 50% |  |  |  | 20 | 3
| (100%) Completion of External works | 50% |  |  |  | 23 | 2
S
| Design fees - 1st instalment | 50% |  |  |  | 1 | 1
| Design fees - balance | 50% |  |  |  | 2 | 11
T
| Monthly project management | 100% |  |  |  | 1 | 24
ESTIMATED MONTHLY VALUATION (EXCL. ADVANCE)
CUMULATIVE VALUATION
DEDUCT RETENTION
CUMULATIVE RETENTION
SUB TOTAL
ADVANCE REPAYMENT
CUMULATIVE ADVANCE REPAYMENT
ESTIMATED MONTHLY PAYMENT
CUMULATIVE MONTHLY PAYMENT
ITEM | DESCRIPTION | AMOUNT
A | AGREED CONTRACT SUM (DISCOUNTED, LESS TAXES)
B | LIMIT OF RETENTION
C | ADVANCE MOBILIZATION (% OF CONTRACT SUM) | 25%
D | RETENTION DEDUCTED PER VALUATION | 10%
E | LIMIT OF RETENTION (% OF CONTRACT SUM) | 5%
F | RETENTION RELEASED AT PRACTICAL COMPLETION | 50%
G | COMMENCEMENT DATE (MONTH 0) | 2026-09-30
H | CONTRACT PERIOD (MONTHS) | 24
J | PRACTICAL COMPLETION DATE
K | DEFECTS LIABILITY PERIOD (MONTHS) | 6
L | END OF DEFECTS LIABILITY PERIOD
M | ADVANCE REPAYMENT STARTS (MONTH NO.) | 3
N | ADVANCE REPAYMENT PERIOD (MONTHS) | 18
CHECK: TOTAL PAYMENT LESS CONTRACT SUM (MUST BE NIL)
NOTES:
1. TAXES NOT INCLUDED
2. PAYMENTS PROJECTED TO BE AT THE END OF THE RESPECTIVE MONTHS.
3. EACH BILL IS SPREAD OVER ITS SUB-ITEMS USING THE START MONTH AND DURATION IN COLUMNS AH AND AI; AMOUNTS LINK TO GEN SUMMARY.
4. RETENTION IS DEDUCTED UNTIL THE LIMIT OF RETENTION IS REACHED; HALF IS RELEASED THE MONTH AFTER PRACTICAL COMPLETION AND THE BALANCE AT THE END OF THE DEFECTS LIABILITY PERIOD.

## GEN SUMMARY.
PROJECT: PROPOSED HEAD OFFICE FOR PRIORITY INSURANCE
LOCATION: RIDGE, ACCRA
CLIENT: PRIORITY INSURANCE
DATE: 07/10/2026 (PRELIMINARY ESTIMATE REV. 6)
ITEM | GENERAL SUMMARY |  | AMOUNT USD | DISCOUNTED AMOUNT USD
A | BILL NO. 1- PRELIMINARIES AND GENERAL ITEMS
B | BILL NO. 2- DEMOLITIONS AND ALTERATIONS |  | 50000
C | BILL NO. 3 -SUBSTRUCTURE (ALL PROVISIONAL)
D | BILL NO. 4 -SUB-BASEMENT FLOOR
E | BILL NO. 5 - GROUND FLOOR
F | BILL NO. 6 - FIRST FLOOR
G | BILL NO. 7- SECOND FLOOR
H | BILL NO. 8 -THIRD FLOOR
J | BILL NO. 9 -FOURTH FLOOR
K | BILL NO. 10 - FIFTH FLOOR
L | BILL NO. 11 - KITCHEN CABINETRY/WALL CLADDING |  | 134515.22
M | BILL NO. 12. PLUMBING, FIRE-FIGHTING AND MECHANICAL
N | BILL NO. 13: ELECTRICAL WORKS
P | BILL NO. 14. EXTERNAL FAÇADE WORKS
Q | BILL NO. 15.- EXTERNAL WORKS (ALL PROVISIONAL) |  | 47193.4355
R | DESIGN FEES |  | 194211.36
S | PROJECT MANAGEMENT FEES
| SUB - TOTAL (1) | US $
LESS: DISCOUNT
| AGREED DISCOUNTED CONTRACT SUM |  | 6250000
| TOTAL COST OF THE WORKS (EXCLUDING TAXES) | US $
SIGNED: ……………………………………………………………
DATE: ………………………………………...........………….