## Slide 1
COMMERCIAL DEPARTMENT · PRE & POST CONTRACT
Outstanding Projects
& Deliverables
Status report to Management
18 SEPTEMBER 2026
22
Deliverables tracked
13
Active projects
77%
Delivered to date
5
Still outstanding
Presented by the Commercial Manager
Notes: Good morning. This is the commercial department status report as at 18 September 2026, covering pre and post contract deliverables across 13 active projects. Twenty-two deliverables are being tracked. Seventeen are complete. Five remain outstanding, and three of those need a decision from this meeting.

## Slide 2
AT A GLANCE
Executive Summary
Position of the commercial deliverables register as at 18 September 2026.
22
Deliverables tracked
Across 13 active projects
17
Delivered
77% of the register
5
Outstanding
4 in progress, 1 not started
3
Need a decision today
Blocked or at risk of slipping
1
The register is 84% complete against a 93% plan
A shortfall of 9 percentage points, equivalent to two full deliverables. All of it sits in three items: Kinbu, Stanbic and Ecole.
2
Two tender submissions fall due on 24 September
The Kinbu School Canteen priced BoQ stands at 10% against a 100% plan, and the Stanbic Bank preliminary estimate at 50%. Both are held by the wider team rather than a named owner.
3
Priority Insurance is held up by missing design information
The architectural take-off is 90% done, but the floor finishes schedule and structural drawings are still outstanding. The budget that follows it cannot start.
Commercial Department · Outstanding Projects & Deliverables · 18 September 2026
2
Notes: Three things to take away. First, we are 84% complete against a 93% plan — a nine point gap, and it is concentrated, not spread. Second, two tenders close on 24 September and one of them, Kinbu, is only 10% priced. Third, Priority Insurance is blocked on information we do not control. Slides four to eight take each of these in turn.

## Slide 3
PORTFOLIO HEALTH
Where the 22 Deliverables Stand
Chart: 
| Delivered | In progress | Not started
Delivery status | 17 | 4 | 1
22
deliverables
Delivered
Signed off and issued
17
77%
In progress
Started but short of the plan
4
18%
Not started
Zero progress, still within plan
1
5%
Progress against plan
Planned
93.2%
Actual
84.1%
9.1 points behind plan — a shortfall of two deliverables
Commercial Department · Outstanding Projects & Deliverables · 18 September 2026
3
Notes: Seventeen of twenty-two deliverables are complete — just over three quarters of the register. Four are in progress and one has not started, though that one is still inside its plan. Measured on progress rather than headcount, we are at 84.1% against a planned 93.2% — a gap of about two deliverables.

## Slide 4
DELIVERY PERFORMANCE
Where the Portfolio Is Behind
The four projects carrying variance. Planned versus actual completion, averaged across each project’s deliverables.
Chart: 
| Priority Insurance | Ecole Int'l School | Stanbic Bank | Kinbu Canteen Tender
Planned | 25 | 100 | 100 | 100
Actual | 20 | 50 | 50 | 10
Priority Insurance shows a small gap because only part of its work was scheduled to be complete by today.
9
projects fully delivered
Seventeen deliverables closed, every one of them at 100% of plan. The detail follows on the next slide.
4
projects behind plan
Between them they account for the entire shortfall of two deliverables against the September plan.
Commercial Department · Outstanding Projects & Deliverables · 18 September 2026
4
Notes: This is where the variance actually sits. Kinbu is the outlier — 10% against a 100% plan. Stanbic and Ecole are both at half of what was planned. Priority Insurance looks small at 20 against 25, and it is small, because only half of its BoQ was ever scheduled to be done by today. Every other project in the portfolio, nine of them, is complete.

## Slide 5
COMPLETED WORK
17 Deliverables Signed Off Across 9 Projects
3
Anglogold Ashanti
Budget
Revised BoQ
Valuation report
Gilbert, Sedem
3
Warehouse
Cost analysis — electrical works
Cashflow forecast
Subcontractor selection — roller shutter
Eunice
3
RE Villa
Budgetary report
Remeasurement of hardcore filling
Cashflow forecast
Eunice
2
Vanguard Assurance Spintex
Monthly valuation
Budgetary report
Gilbert
2
Advans Savings & Loans
Final account
Budgetary report
Tracy
1
Thoroughbred Place
Financial report (internal)
Sedem
1
Barry Callebaut
Budgetary report
Gilbert
1
Brimmo Gardens Tender
RFP submission
Eunice
1
Enterprise COO's Office
Cashflow forecast
Eunice
Commercial Department · Outstanding Projects & Deliverables · 18 September 2026
5
Notes: This is the delivered column. Nine projects are fully closed out for the period — seventeen deliverables in total. Anglogold, the Warehouse and RE Villa each carried three. Worth noting that the Anglogold budget is finished but is sitting with a reviewer; I will come back to that on the blockers slide.

## Slide 6
THE WATCH LIST
5 Outstanding Deliverables
Ordered by exposure. The dark marker on each bar shows where the deliverable was planned to be today.
Kinbu School Canteen Tender
Priced BoQ
Actual 10%
Planned 100%
DUE
24 Sep 2026
OWNER
Team
CRITICAL
Stanbic Bank
Preliminary Estimate
Actual 50%
Planned 100%
DUE
24 Sep 2026
OWNER
Team
AT RISK
Ecole International School
BoQ and Budget
Actual 50%
Planned 100%
DUE
18 Sep 2026
OWNER
Tracy, Obed, Eunice
DUE TODAY
Priority Insurance
Complete BoQ
Actual 40%
Planned 50%
DUE
30 Sep 2026
OWNER
Obed, Sedem, Gilbert
BLOCKED
Priority Insurance
Complete Budget
Actual 0%
Planned 0%
DUE
09 Oct 2026
OWNER
Obed, Sedem, Gilbert
ON PLAN
Commercial Department · Outstanding Projects & Deliverables · 18 September 2026
6
Notes: Five items. Kinbu is the one that should worry us — 10% priced with six days to submission. Stanbic is at half. Ecole was due today and is at half. Priority Insurance BoQ is only ten points behind plan, but it is blocked rather than late. The Priority budget has not started and does not need to have — it follows the BoQ.

## Slide 7
WHAT FALLS DUE NEXT
The Next Three Weeks
Every outstanding deliverable lands between today and 9 October.
Ecole Int'l School
BoQ and Budget
50% complete
18 Sep
Today
Kinbu Canteen Tender
Priced BoQ
10% complete
Stanbic Bank
Preliminary Estimate
50% complete
24 Sep
In 6 days
Priority Insurance
Complete BoQ
40% complete
30 Sep
In 12 days
Priority Insurance
Complete Budget
Not started
09 Oct
In 21 days
Pinch point
Two tender submissions close on the same day, 24 September, and both sit with the team rather than a named owner. Between them they account for 1.4 of the 2.0 deliverables we are behind. Naming an owner for each is the single highest-value action available this week.
Commercial Department · Outstanding Projects & Deliverables · 18 September 2026
7
Notes: Laid out on a calendar, the exposure is obvious. Today Ecole is due. Six days from now two tenders close on the same day. The Priority BoQ follows on the thirtieth and its budget on the ninth of October. The twenty-fourth is the pinch point, and neither of those two tenders has a named owner.

## Slide 8
ESCALATION
Blockers and Decisions Required
Three items cannot be cleared by the commercial department alone.
1
Tender capacity
Kinbu School Canteen · Stanbic Bank
Both submissions close on 24 September. The Kinbu priced BoQ is at 10% and the Stanbic estimate at 50%. Neither has a named owner — both are logged against "Team".
DECISION REQUIRED
Assign a named lead to each tender today, or authorise a request for an extension on Kinbu.
2
Missing design information
Priority Insurance
The architectural take-off is 90% done. The floor finishes schedule and the structural drawings have not been received, so the BoQ cannot be closed and the budget behind it cannot start.
DECISION REQUIRED
Escalate to the design team and the client for a firm issue date for both documents.
3
Review bottleneck
Anglogold Ashanti
The budget is complete and has been sitting in "awaiting review" since 11 September. It is the only finished deliverable not yet signed off.
DECISION REQUIRED
Nominate the reviewer and set a clearance date so the deliverable can be closed.
What we need from this meeting
Two named tender leads, a firm issue date for the Priority Insurance drawings, and a nominated reviewer for the Anglogold budget.
Commercial Department · Outstanding Projects & Deliverables · 18 September 2026
8
Notes: These are the three asks. One: name a lead for each of the two tenders, or let us request an extension on Kinbu. Two: help us get a firm date for the Priority Insurance floor finishes schedule and structural drawings. Three: tell us who reviews the Anglogold budget and by when. All three are decisions, not work.

## Slide 9
RESOURCING
Workload Across the Team
Deliverables held by each team member, split between delivered and outstanding.
Chart: 
| Team | Obed | Tracy | Sedem | Gilbert | Eunice
Delivered | 0 | 0 | 2 | 3 | 4 | 8
Outstanding | 2 | 3 | 1 | 2 | 2 | 1
Eunice carries the largest load
Nine deliverables, eight of them already closed. The highest throughput in the department.
Obed has no closed deliverables
All three of his items are shared and still open — Priority Insurance and Ecole. Worth checking whether he is blocked rather than behind.
Two items have no named owner
Both Kinbu and Stanbic are logged against "Team". These are the two tenders closing on 24 September.
Shared deliverables count once for each named owner, so the totals here (28) exceed the 22 items on the register. "Team" means no individual was named.
Commercial Department · Outstanding Projects & Deliverables · 18 September 2026
9
Notes: On resourcing: Eunice is carrying nine deliverables and has closed eight. Gilbert six, Sedem five. Obed shows three open and none closed, but all three are shared items on blocked projects, so that is a blockage rather than a performance question. The two unowned items are the same two tenders we keep coming back to.

## Slide 10
NEXT STEPS
Closing the Nine-Point Gap
1
Name a lead for each open tender
Kinbu priced BoQ and Stanbic preliminary estimate
OWNER
Commercial Manager
BY
Today
2
Close out the Ecole BoQ and budget
Now at 50% and past its due date
OWNER
Tracy, Obed, Eunice
BY
22 Sep
3
Obtain the Priority Insurance drawings
Floor finishes schedule and structural drawings
OWNER
Design team / client
BY
23 Sep
4
Clear the Anglogold budget review
Complete since 11 September, awaiting a reviewer
OWNER
Nominated reviewer
BY
22 Sep
Clearing items 1 and 2 alone returns the register to plan.
Source: Commercial Department deliverables register (22 rows), 18 September 2026. Dates read as day/month/year. Deliverable names lightly corrected for spelling.
Notes: To close: four actions. Name the two tender leads today. Finish Ecole by the twenty-second. Chase the Priority Insurance drawings by the twenty-third. Clear the Anglogold review by the twenty-second. Items one and two on their own take us back to plan. I need decisions on the tender ownership and the drawings before we leave this room.