## 18-09-2025
COMMERCIAL DEPARTMENT OUTSTANDING PROJECTS
2026-09-18
PRE & POST CONTRACT
PROJECT TITLE | DELIVERABLES | EXPECTED FINISH DATE | PLANNED | ACTUAL | PERSON RESPONSIBLE | RREMARKS
Priority Insurance | Complete BOQ | 2026-09-30 | 50% | 40% | Obed Sedem Gilbert | Take Off of Architectural drawing 90% completed, awaiting floor finishes schedule and structural drawing
| Complete Budget | 2026-10-09 | 0% | 0%
Stanbic Bank | Preliminary Estimate | 24/09/2026 | 100% | 50% | Team
Ecole International school | BoQ and Budget | 18/09/2026 | 100% | 100% | Tracy Obed Eunice
Thoroughbred Place | Financial Report (internal) | 14/9/2026 | 100% | 100% | Sedem
Vanguard Assurance Spintex | Monthly Valuation | 2026-11-09 | 100% | 100% | Gilbert
| Budgetary Report | 2026-11-09 | 100% | 100% | Gilbert
Barry Callebaut | Budgetary Report | 2026-11-09 | 100% | 100% | Gilbert
Kinbu School Canteen Tender | Priced BoQ | 24/09/2026 | 100% | 10% | Team
Anglogold Ashanti | Budget | 2026-09-11 | 100% | 100% | Gilbert | Awaiting Review
Anglogold Ashanti | Revised BOQ | 14/09/2026 | 100% | 100% | Sedem
Anglogold Ashanti | Valuation Report | 16/09/2026 | 100% | 100% | Sedem
Advans Savings and Loans | Final Account | 2026-09-11 | 100% | 100% | Tracy
| Budgetary Report | 2026-09-11 | 100% | 100%
Brimmo Gardens tender | RFP Submission | 14/09/2026 | 100% | 100% | Eunice
Warehouse | Cost analysis for electrical works | 2026-09-11 | 100% | 100% | Eunice
| Cashflow forecast | 2026-09-11 | 100% | 100%
| Subcontractor selectioln for roller shutter | 2026-09-11 | 100% | 100%
RE Villa | Budgetary Report | 2026-09-14 | 100% | 100% | Eunice
| Remeasurement of hardcore filing | 2026-09-11 | 100% | 100%
| Cashflow forecast | 2026-09-11 | 100% | 100%
Enterprise COO's Office | Cashflow forecast | 2026-09-11 | 100% | 100% | Eunice