## Slide 1
COMMERCIAL DEPARTMENT · PRE & POST CONTRACT
Outstanding Projects
& Deliverables
Weekly status report to Management
25 SEPTEMBER 2026
8
Live deliverables
6
Active projects
75%
Delivered
5
Awaiting review
Presented by the Commercial Manager
Notes: Good morning. This is the weekly commercial status as at 25 September. The register now carries eight live deliverables across six projects. Six are finished. The headline this week is good news on the tenders and a growing queue in review.

## Slide 2
AT A GLANCE
Executive Summary
Position of the commercial deliverables register as at 25 September 2026.
8
Live deliverables
Across 6 active projects
6
Delivered
75% of the register
5
Awaiting review
Finished but not signed off
2
Still open
Both on Priority Insurance
1
Both tenders that were at risk last week have landed
The Kinbu priced BoQ moved from 10% to finished and the Stanbic submission from 50% to two completed documents. Neither missed its 25 September deadline.
2
Five of the six finished deliverables are sitting in review
Nothing can be closed out until a reviewer signs it off. The Advans final account has been waiting fourteen days, the oldest item in the queue.
3
Priority Insurance has not moved in seven days
Still at 40% against a 50% plan. The floor finishes schedule and structural drawings raised last week have not arrived, so the budget behind it still cannot start.
Commercial Department · Outstanding Projects & Deliverables · 25 September 2026
2
Notes: Three things this week. First, the two tenders we flagged as critical last Friday both went in on time, which clears the largest gap on the register. Second, the problem has moved rather than gone away: five finished deliverables are now stuck waiting for a reviewer. Third, Priority Insurance is exactly where it was seven days ago, because the information we asked for has not come.

## Slide 3
PORTFOLIO HEALTH
Where the 8 Deliverables Stand
Chart: 
| Delivered | In progress | Not started
Delivery status | 6 | 1 | 1
8
deliverables
Delivered
Finished; 5 of these await review
6
75%
In progress
Priority Insurance BoQ, at 40%
1
12.5%
Not started
Priority Insurance budget, on plan
1
12.5%
Progress against plan
Planned
81.3%
Actual
80.0%
1.3 points behind plan — the register is effectively on schedule
Commercial Department · Outstanding Projects & Deliverables · 25 September 2026
3
Notes: Six of the eight live deliverables are finished. One is in progress and one has not started, and both of those are Priority Insurance. On progress rather than headcount we are at 80.0% against a planned 81.3%, so about one tenth of a deliverable behind. On the numbers the register is on schedule. The issue is not delivery this week, it is sign-off.

## Slide 4
MOVEMENT
What Changed Since 18 September
Actual completion of every deliverable carried over from last week’s register.
Chart: 
| Priority Ins. — Complete Budget | Priority Ins. — Complete BoQ | Stanbic — tender submission | Kinbu — Priced BoQ
18 September | 0 | 40 | 50 | 10
25 September | 0 | 40 | 100 | 100
The register carries live work only. Seventeen deliverables closed last week were removed from it, so the portfolio percentages on slide 3 are not comparable week to week — the comparison above is per deliverable.
Stanbic was recorded last week as a single “Preliminary Estimate” and this week as two documents, “Cost Proposal” and “Relevant Experience and CV”. It is shown here as one submission.
2
tenders closed on time
Kinbu and Stanbic both went in by 25 September, clearing the two largest gaps on last week’s register.
0
points of movement
Priority Insurance is unchanged at 40% seven days on, still waiting on the same two documents.
Commercial Department · Outstanding Projects & Deliverables · 25 September 2026
4
Notes: This is the week on week picture. Kinbu went from ten per cent to finished, Stanbic from half to two completed documents. Those were the two items I flagged as critical last Friday, and both landed. Priority Insurance is the flat line: forty per cent last week, forty per cent today. One caution on the numbers, the register only lists live work, so the overall percentages are not comparable between weeks. That is why this chart compares individual deliverables.

## Slide 5
COMPLETED WORK
6 Deliverables Finished Across 5 Projects
2
Stanbic Bank
Cost Proposal
Relevant Experience and CV
AWAITING REVIEW
Team
1
Kinbu School Canteen Tender
Priced BoQ
AWAITING REVIEW
Team
1
Ecole International School
BoQ and Budget
AWAITING REVIEW
Tracy, Obed, Eunice
1
Advans Savings & Loans
Final Account
AWAITING REVIEW
Tracy
1
Thoroughbred Place
Financial Report (external)
COMPLETE
Sedem
Commercial Department · Outstanding Projects & Deliverables · 25 September 2026
5
Notes: Six deliverables finished across five projects. The tender team carried three of them. Note the amber chips: five of these six are complete but have not been signed off. Only the Thoroughbred financial report is clear of the review queue.

## Slide 6
THE BOTTLENECK
5 Deliverables Waiting on Review
Finished work that cannot be closed out. Waiting time is measured from the expected finish date.
Advans Savings & Loans
Final Account
OWNER
Tracy
EXPECTED FINISH
11 Sep 2026
WAITING
14 days
Ecole International School
BoQ and Budget
OWNER
Tracy, Obed, Eunice
EXPECTED FINISH
18 Sep 2026
WAITING
7 days
Stanbic Bank
Cost Proposal
OWNER
Team
EXPECTED FINISH
25 Sep 2026
WAITING
Submitted today
Stanbic Bank
Relevant Experience and CV
OWNER
Team
EXPECTED FINISH
25 Sep 2026
WAITING
Submitted today
Kinbu School Canteen Tender
Priced BoQ
OWNER
Team
EXPECTED FINISH
25 Sep 2026
WAITING
Submitted today
Commercial Department · Outstanding Projects & Deliverables · 25 September 2026
6
Notes: This is the slide I most want a decision on. Five finished deliverables are waiting for a reviewer. The Advans final account has been waiting a fortnight, Ecole a week, and the three tender documents went in today so they are not yet late. None of this work can be closed out, and the two oldest are holding up projects we would otherwise report as finished.

## Slide 7
THE WATCH LIST
2 Deliverables Still Open
Both sit on Priority Insurance. The dark marker shows where each was planned to be today.
Priority Insurance
Complete BoQ
Actual 40%
Planned 50%
DUE
30 Sep 2026
OWNER
Obed, Sedem, Gilbert
BLOCKED
Priority Insurance
Complete Budget
Actual 0%
Planned 0%
DUE
09 Oct 2026
OWNER
Obed, Sedem, Gilbert
ON PLAN
Why it has not moved
The architectural take-off has been 90% complete for two weeks. The floor finishes schedule and the structural drawings have still not been issued, so the BoQ cannot be closed. The budget is sequenced behind the BoQ, which is why it correctly shows no progress against a zero plan rather than a slippage.
Ask: a firm issue date for both documents from the design team and the client.
Commercial Department · Outstanding Projects & Deliverables · 25 September 2026
7
Notes: Only two deliverables are still open and both belong to Priority Insurance. The BoQ is ten points behind plan, which is small, but it has not moved at all in seven days because we are waiting on the same two drawings I raised last week. The budget sits behind it and is correctly showing nothing against a zero plan, so it is not late yet, but it will be if the drawings do not come.

## Slide 8
ESCALATION
Blockers and Decisions Required
Two items cannot be cleared by the commercial department alone.
1
Review bottleneck
Stanbic · Kinbu · Ecole · Advans
Five finished deliverables across four projects are waiting to be signed off. The Advans final account has been in the queue fourteen days and Ecole seven. Three more went in today, so the queue will grow again next week unless it is cleared. Until each is reviewed the work cannot be closed out or reported as complete.
DECISION REQUIRED
Nominate a reviewer for each of the five, and set a clearance date for the two that are already overdue.
2
Missing design information
Priority Insurance
The same two documents raised last week, the floor finishes schedule and the structural drawings, have still not been issued. The architectural take-off has been stuck at 90% for a fortnight. The BoQ is now the only deliverable on the register making no progress, and the budget behind it cannot start.
DECISION REQUIRED
Escalate to the design team and client for a firm issue date. Agree a revised BoQ date if they slip past 30 September.
What we need from this meeting
A named reviewer against each of the five items in the queue, and a firm issue date for the two Priority Insurance drawings.
Commercial Department · Outstanding Projects & Deliverables · 25 September 2026
8
Notes: Two asks. First, the review queue: I need a named reviewer against each of the five items, and a date for the Advans and Ecole ones that are already overdue. Second, the Priority Insurance drawings, which is the same ask as last week and has not been actioned. If those drawings will not arrive before the thirtieth I would rather agree a revised BoQ date now than report a slippage next Friday.

## Slide 9
RESOURCING
Workload Across the Team
Live deliverables held by each team member, split between finished and still open.
Chart: 
| Eunice | Gilbert | Tracy | Obed | Sedem | Team
Finished | 1 | 0 | 2 | 1 | 1 | 3
Still open | 0 | 2 | 0 | 2 | 2 | 0
The tender team cleared everything
All three items held against "Team", both Stanbic documents and the Kinbu priced BoQ, were finished this week.
Gilbert has nothing finished
Both of his items are the Priority Insurance BoQ and budget. That is a blockage on drawings, not a delivery problem.
One project holds every open item
Priority Insurance accounts for all four open entries shown here, across Obed, Sedem and Gilbert.
Shared deliverables count once for each named owner, so the totals here (14) exceed the 8 items on the register. "Team" means no individual was named.
Source: Commercial Department deliverables register, 25 September 2026. Dates read as day/month/year. The register gives the Stanbic "Relevant Experience and CV" finish date as 25 September 2027; it is read here as 2026.
Commercial Department · Outstanding Projects & Deliverables · 25 September 2026
9
Notes: On resourcing: the tender team cleared all three of its items this week. Tracy and Eunice are clear. Gilbert, Obed and Sedem carry the four open entries between them, and every one of those is Priority Insurance. So the department has capacity once the review queue clears. One data note, the register gives a 2027 finish date against one of the Stanbic documents; I have read that as this year.