## 25-09-2025
COMMERCIAL DEPARTMENT OUTSTANDING PROJECTS
2026-09-25
PRE & POST CONTRACT
PROJECT TITLE | DELIVERABLES | EXPECTED FINISH DATE | PLANNED | ACTUAL | PERSON RESPONSIBLE | RREMARKS
Priority Insurance | Complete BOQ | 2026-09-30 | 50% | 40% | Obed Sedem Gilbert | Take Off of Architectural drawing 90% completed, awaiting floor finishes schedule and structural drawing
| Complete Budget | 2026-10-09 | 0% | 0%
Stanbic Bank | Cost Proposal | 2026-09-25 | 100% | 100% | Team | Awaiting Review
| Relevant Experience and CV | 2027-09-25 | 100% | 100%
Kinbu School Canteen Tender | Priced BoQ | 2026-09-25 | 100% | 100% | Team | Awaiting Review
Ecole International school | BoQ and Budget | 18/09/2026 | 100% | 100% | Tracy Obed Eunice | Awaiting Review
Thoroughbred Place | Financial Report (external) | 14/9/2026 | 100% | 100% | Sedem
Advans Savings and Loans | Final Account | 2026-09-11 | 100% | 100% | Tracy | Awaiting Review