## Verification Notes
BOQ VERIFICATION - PROPOSED KANESHIE BLOCK N REDEVELOPMENT
Drawings used: Structural SHC-KANESHIE-STR-000 to 107 (108 sheets); Architectural SHC-NORTH K-ARCH-101 to 606 (59 sheets).
HOW TO READ THE BOQ SHEETS
Column C = original BOQ quantity (unchanged). Column D "Verified Qty" (green) = quantity measured from the drawings; it links to the Verification Take-off sheet where every calculation is shown.
Column F "Verified Unit": red where the unit has been corrected (e.g. edges of bed m2 -> m; hinges nr -> pairs; provisional sums -> item).
Description text in red "[PER DRAWINGS: ...]" = the drawings describe the item differently; the original description is kept above it.
Rows shaded yellow (item codes N1..N12, A1, D1, W, X) are ADDED items omitted from the BOQ. They sit inside the existing page totals.
Column H "Amount" now = Rate x Verified Qty. Column I gives remarks.
KEY FINDINGS
1. Superstructure columns: BOQ multiplies concrete, formwork and reinforcement by 5. The base figures already represent all floors - the x5 overstates them five-fold.
2. Concrete walls (306 m3) understate the shear/lift/emergency core walls (c.667 m3 measured). The formwork formula refers to the column line.
3. Beams (c.211 m3 concrete, c.111 t steel, c.2,100 m2 formwork), Y20 wall bars (82 t), raft edge formwork, slab edges and stair formwork are not in the BOQ - added.
4. Lintels 360 m3 is excessive - lintels over all scheduled openings measure c.56 m3. Suspended slabs measure c.3,326 m3 (BOQ 2,790); slab reinforcement Y12 586 t (BOQ 315 t) per the bar bending schedules.
5. Doors and windows: quantities agree with the schedules except DW2 (1 nr, BOQ 2). Several door descriptions are mismatched with the schedule (fire ratings / leaf types) - corrected in red.
6. Floor tiles: the tile sizes in the BOQ read "60x60mm" etc. - drawings are 600x600mm. 60x120 tile is a FLOOR tile to lobbies (legend), not wall. PU resin to parking decks and wall tiles to washrooms are not billed - added.
MEASUREMENT METHOD
Slab areas, slab perimeters and beam lengths were measured directly from the structural GA sheets (vector/raster geometry calibrated on grid 1-12 = 36,500 mm and A1-Q = 34,350 mm).
Block wall lengths were measured from the architectural floor plans at 1:100 (wall outlines converted to centre-lines; door/window gaps excluded). Wall thickness classes: <=210mm band = 150 walls, 210-245 = 200 walls, >245 = RC core walls (excluded from blockwork).
Floor finishes: rooms segmented from the plans and classified by room label (washroom, corridor, bedroom...) using the tiling-layout legend; manual corrections are listed on the take-off sheet.
Reinforcement quantities come from the separate Reinforcement Take-off workbook (bar bending schedules, 1,306 t total).
Measured quantities are net (no waste). Measurement by digital scaling is accurate to about +/-3-5% on walls and finishes; check critical items before tender.
QUERIES FOR THE DESIGN TEAM (RFI)
a) Raft section A-A shows 2,700 of fill below the raft but levels (-1.000 raft top, -4.000 formation) give 1,700.
b) No GF slab / bed detail on structural drawings (BOQ items J, K).
c) Architectural M1/M2/M3 levels are 300 mm above structural SSLs (+2800/+5500/+8200 vs +2500/+5200/+7900).
d) Service/goods lift: only two lift shafts are shown.
e) Wall-tile height in washrooms, roof drainage layout and burglar-proofing extent are not dimensioned.

## Prelims
Item | Description | Qty | Unit | Rate | Amount
BILL NO. 1- PRELIMINARIES AND GENERAL CONDITIONS
NAME: PROPOSED KANESHIE BLOCK N REDEVELOPMENT
CLIENT/ CONSULTANTS: STATE HOUSING PROJECT
CONTRACTOR: FBC PARTNERS GHANA LTD
DRAWING: STRUCTURAL, ARCHITECTURAL, MEP DRAWINGS - KANESHIE BLOCK N REDEVELOPMENT
(The Contractor is free to price for additional items under Preliminaries not included in the List below)
A | Performance Security
B | Offices for use by Contractor
C | Offices for use by the Engineer
D | Watching and Protection of the Works
E | Transport for Workpeople
F | First Aid Equipment
G | Project Signboard
H | Setting Out of the Works
J | Agent or Foreman-in-Charge
K | Plant, tools and Vehicles
L | Branded PPEs
M | Security and protection
N | All facilities, temporary works and services
P | Allow for providing all scaffolding, and apparatus
profiles and apparatus generraly required for the
proper execution of the Works. The Contractor
shall provide without extra charge all labour and
equipment or apparatus required by the Engineer
for the testing and measuring the Works and for
weighing, proving or testing the efficiency of any
portion of the Works
Q | Water for the works
BILL NO. 1
GENERAL ITEMS (PRELIMINARIES)
Carried to General Summay

## structural works
Item | Description | Qty | Verified Qty | Unit | Verified Unit | Rate | Amount | Verification remarks
PROPOSED KANESHIE BLOCK N REDEVELOPMENT
SUBSTRUCTURE
D GROUNDWORK (D20 EXCAVATION)
Site Preparation
A | Clear site of all vegetation, grub up their roots and dispose-off | 2369 | 2299.0095 | m2 | m2 |  | 0 | Plot + Parking-22 forecourt
B | Excavate oversite to remove vegetable soil average 150mm deep and deposit on site for re-use average 50m from excavation. | 1477 | 1800 | m2 | m2 |  | 0 | BOQ 1,477 m2 = raft only; excavation footprint 45 x 40 m
C | Excavate raft foundation to reduce levels maximum depth 4.00m | 6055.7 | 7200 | m3 | m3 |  | 0
D | Fill to make up levels thickness 1300mm with waterproof external membrane with high strength biaxial geogridover geotextile 300mm thick [PER DRAWINGS: fill over raft is c.1.0m thick (raft top -1.000 to underside of hardcore -0.000)] | 1624.7 | 1445.3447 | m3 | m3 |  | 0 | BOQ uses 1.1 x oversite area
E | Fill to make up levels thickness 1300mm with 300mm thick compacted crushed rock layers between layers until formation level and well compacted [PER DRAWINGS: crushed rock/geogrid layers are c.1,700 thick between raft underside (-2.300) and formation (-4.000)] | 1920.1 | 3060 | m3 | m3 |  | 0 | RFI: Section A-A dims show 2,700
Backfill and compact selected material around
F | foundations | 1255 | 745.2 | m3 | m3 |  | 0
Load up surplus excavated material
G | and remove from site | 3799.2 | 6454.8 | m3 | m3 |  | 0
Hardcore Filling
H | Approved imported granular material
Filling to make up levels: depositing and
compacting in layers 150mm maximum
| thickness | 221.55 | 221.4 | m3 | m3 |  | 0
E10 IN SITU CONCRETE
Concreteworks
Plain in-situ concrete(1:4:8-38mmAggre)
as described in:
J | Blinding [PER DRAWINGS: blinding minimum 100mm thick (General Notes item 1.0/3)] | 73.85 | 147.6 | m3 | m3 |  | 0
K | 150mm thick Bed | 221.55 | 221.4 | m3 | m3 |  | 0 | No GF slab detail issued - RFI
| TO COLLECTION | [5 empty] | 0
Item | Description | Qty | Verified Qty | Unit | Verified Unit | Rate | Amount | Verification remarks
E10 IN SITU CONCRETE
Vibrated in situ concrete C40
as described in:
A | Concrete walls | 34 | 22.5696 | m3 | m3 |  | 0
B | Concrete in raft | 1920.1 | 1918.8 | m3 | m3 |  | 0
C | Concrete in columns | 7 | 17.2819 | m3 | m3 |  | 0 | BOQ 7 m3 too low: 35 columns x 1.3m
E30 REINFORCEMENT
High Tensile yield round bar reinforcement (standard)
D | 20mm in raft | 2.467 | 2.466 | t | t |  | 0
E | 25mm diameter in raft | 180 | 184.672 | t | t |  | 0
F | 10mm diamter for concrete [PER DRAWINGS: Y10 links to columns & walls (raft to GF)] | 2.574 | 4.029 | t | t |  | 0
G | 12mm diamter for concrete [PER DRAWINGS: Y12 to walls (raft to GF)] | 1.566 | 1.253 | t | t |  | 0
H | 25mm diamter for concrete [PER DRAWINGS: Y25 to columns & walls (raft to GF)] | 1.414 | 21.306 | t | t |  | 0
E20 FORMWORK
| Concrete Walls | 137 | 180.557 | m2 | m2 |  | 0 | Both faces, 1.3m high
J | Edges of bed 150mm wide [PER DRAWINGS: edge 150mm high - measured in linear metres] | 154 | 154 | m2 | m |  | 0 | Unit corrected m2 -> m (edge not exceeding 250mm)
N1 | Y20 in columns (raft to GF) |  | 0.338 | - | t |  | 0
N2 | Formwork to edges of raft 1300mm high |  | 200.2 | - | m2 |  | 0
BLOCK WORK
K | 150mm walls to plinth | 202 | 200.2 | m2 | m2 |  | 0
N3 | Formwork to sides of columns (raft to GF) |  | 136.955 | - | m2 |  | 0
| TO COLLECTION | [5 empty] | 0
COLLECTION
| Page 1 | [5 empty] | 0
| Page 2 | [5 empty] | 0
| SUBSTRUCTURE TO SUMMARY | [5 empty] | 0
Item | Description | Qty | Verified Qty | Unit | Verified Unit | Rate | Amount | Verification remarks
E10 IN SITU CONCRETE
CONCRTRE WORK
REINFORCED IN-SITU CONCRTE
Vibrated in- situ concreteC40
as described in:
A | Lintel [PER DRAWINGS: lintels 150x225 over all door/window openings] | 360 | 56.4131 | m3 | m3 |  | 0 | BOQ 5 x 72 = 360 m3 is excessive
B | Columns | 1770 | 433.4563 | m3 | m3 |  | 0 | BOQ multiplies by 5 in error; measured all floors
C | Concrete wall | 306 | 667.3879 | m3 | m3 |  | 0 | Shear, lift & emergency core walls all floors
D | Stairs | 120 | 124.5299 | m3 | m3 |  | 0
E | Suspended slab | 2790 | 3325.765 | m3 | m3 |  | 0
F | Coppings | 15 | 13.716 | m3 | m3 |  | 0
E30 REINFORCEMENT
High Tensile yield round bar reinforcement (standard)
G | 10mm Diameter in columns | 281.655 | 48.472 | t | t |  | 0 | BOQ x5 multiplier is an error - figure already covers all floors
H | 20mm Diameter in columns | 295.73 | 56.589 | t | t |  | 0 | BOQ x5 multiplier is an error
J | 25mm Diameter in columns | 146.875 | 29.946 | t | t |  | 0 | BOQ x5 multiplier is an error
K | 10mm diameter in stairs [PER DRAWINGS: stairs use 12mm (Y12) and 16mm bars - no 10mm in stair BBS] | 8.548 | 10.116 | t | t |  | 0
L | 16mm diameter in stairs | 19.878 | 16.226 | t | t |  | 0
M | 10mm diamter for concrete [PER DRAWINGS: 10mm links in shear & lift walls] | 23.166 | 26.193 | t | t |  | 0
N | 12mm diamter for concrete [PER DRAWINGS: 12mm horizontal bars in shear, lift & ramp walls] | 14.094 | 36.327 | t | t |  | 0
P | 25mm diamter for concrete [PER DRAWINGS: 25mm vertical bars in shear & lift walls] | 12.726 | 77.017 | t | t |  | 0
Q | 12mm diameter for suspended slab | 315 | 586.267 | t | t |  | 0
R | 16mm diameter for suspended slab | 51 | 11.42 | t | t |  | 0
E20 FORMWORK
Formwork as described to:
S | Side and soffits of Lintel / copping | 1200 | 1094.34 | m2 | m2 |  | 0
T | Columns | 7791 | 3440.5275 | m2 | m2 |  | 0 | BOQ x5 multiplier is an error
U | Suspended slab | 12402 | 13380.1 | m2 | m2 |  | 0
V | Concrete wall | 7080 | 5339.103 | m2 | m2 |  | 0 | BOQ formula =C98/0.25 refers to column concrete - error
N4 | Vibrated in-situ concrete C40 in beams (downstands) |  | 210.697 | - | m3 |  | 0 | ADDED - omitted from BOQ
N5 | 20mm diameter in shear & lift walls |  | 82.152 | - | t |  | 0 | ADDED - omitted from BOQ
N6 | 10mm diameter in beams (links) |  | 19.686 | - | t |  | 0 | ADDED - omitted from BOQ
N7 | 16mm diameter in beams |  | 14.785 | - | t |  | 0 | ADDED - omitted from BOQ
N8 | 20mm diameter in beams |  | 22.563 | - | t |  | 0 | ADDED - omitted from BOQ
N9 | 25mm diameter in beams |  | 54.392 | - | t |  | 0 | ADDED - omitted from BOQ
N10 | Formwork to sides and soffits of beams |  | 2097.75 | - | m2 |  | 0 | ADDED - omitted from BOQ
N11 | Formwork to edges of suspended slabs 250mm high |  | 3734.1 | - | m |  | 0 | ADDED - omitted from BOQ
N12 | Formwork to soffits of stair flights, landings and risers |  | 731.8608 | - | m2 |  | 0 | ADDED - omitted from BOQ
| REINFORCEMENT CONCRETE WORKS TO SUMMARY | [5 empty] | 0
Item | Description | Qty | Verified Qty | Unit | Verified Unit | Rate | Amount | Verification remarks
GENERAL SUMMARY
A | SUBSTRUCTURE | [5 empty] | 0
B | SUPERSTRUCTURE | [5 empty] | 0
| TOTAL | [5 empty] | 0
BLOCKWORK TO SUMMARY

## architectural works
Item | Description | Qty | Verified Qty | Unit | Verified Unit | Rate | Amount | Verification remarks
PROPOSED KANESHIE BLOCK N REDEVELOPMENT
SUPERSTRUCTURE
F10 BRICK/BLOCK WALL
Blockwork
Walls and Partitions
Solid sancrete blockwork in Cement and Sand
(1:4) mortar as described in:
A | 150mm thick wall | 17500 | 14110.5321 | m2 | m2 |  | 0
A1 | 200mm thick wall |  | 1744.1391 | - | m2 |  | 0 | ADDED - 200/225 walls on plans
Finishing
Walls and Ceilings
12.5mm Cement and sand (1:3) rendering
as described on blockwork or concrete to
B | Interior walls | 26400 | 17036.5327 | m2 | m2 |  | 0
C | Interior partitions and washrooms | 950 | 2964.8897 | m2 | m2 |  | 0
Cement and Sand(1:3) mortar as described
D | 25mm Screeded finish laid level on concrete and
| finished smooth with steel trowel | 17600 | 7644.2 | m2 | m2 |  | 0 | BOQ 17,600 m2 appears to be gross slab area; screed measured to tiled floors
D1 | 12.5mm cement & sand (1:3) rendering to external walls |  | 7081.575 | - | m2 |  | 0 | ADDED - no external render item in BOQ
Painting and decorating
Prepare and apply two undercoat and finishing
coat of Emulsion Paint on:
E | Interior walls | 26400 | 17036.5327 | m2 | m2 |  | 0
F | Interior partitions and washrooms | 950 | 688.0082 | m2 | m2 |  | 0
G | Exterior walls | 5200 | 7081.575 | m2 | m2 |  | 0
H | Ditto to columns and walls not exceeding 300mm girth [PER DRAWINGS: columns are girth exceeding 300mm - measured in m2 (exposed faces GF & parking levels)] | 700 | 948.5 | m2 | m2 |  | 0
J | Ditto soffit of plaster board | 6800 | 7109 | m2 | m2 |  | 0
K | Ditto soffit of plaster board for washrooms | 900 | 493 | m2 | m2 |  | 0
Prepare and apply one coat of Aluminum Primer on
Joinery before fixing to:
Knot, Prime, Stop and apply two undercoats and
one finishing coat of Gloss Oil Paint on:
L | General surfaces of woodwork | 1078 | 1517.115 | m2 | m2 |  | 0
Primer
Mild steel burglar proof bars not exceeding
M | 300mm girth [PER DRAWINGS: measured over area of window openings] | 2102 | 809.4 | m2 | m2 |  | 0
BEDS AND BACKINGS
Cement and sand (1:4) as discribed
N | 12mm Screeded backing to receive wall tiles(m/s) | 1846 | 2276.8816 | m² | m² |  | 0 | Wall tiling height assumed 2.4m
P | 12mm Screeded bed laid level on concrete floor bed receive floor tiles(m/s) | 801 | 8342.48 | m2 | m2 |  | 0 | BOQ =9*89 (801) far too low
TILES
Q | 400x400mm non-slip porcelain floor tiles, adhesive, grout and cutting [PER DRAWINGS: 400x400 non-slip porcelain to washrooms & WCs (legend ARCH-401..409)] | 3150 | 493 | m2 | m2 |  | 0
R | 50x50mm matte R11 porcelain tiles to wet/service areas [PER DRAWINGS: 50x50 matte R11 porcelain to staircases (treads, risers & landings)] | 950 | 698.28 | m2 | m2 |  | 0
S | 60x60mm semi-polished porcelain tiles [PER DRAWINGS: 600x600 semi-polished porcelain to habitable rooms, shops & offices (BOQ "60x60mm" should read 600x600mm)] | 3750 | 4573.9 | m2 | m2 |  | 0
T | 60x120mm semi-polished porcelain tiles (wall) [PER DRAWINGS: 600x1200 semi-polished porcelain FLOOR tiles to stair/lift lobbies & reception - legend shows floor, not wall] | 850 | 357.4 | m2 | m2 |  | 0
U | 60x60mm non-slip R11 porcelain tiles to external/wet areas [PER DRAWINGS: 600x600 non-slip R11 porcelain to corridors, terraces, verandah & service rooms] | 860 | 2219.9 | m2 | m2 |  | 0
V | Interlocking composite tiles to designated external/terrace areas [PER DRAWINGS: interlocking composite tiles to roof-top outdoor sitting & 9th floor play area (ARCH-601..606)] | 650 | 750.5 | m2 | m2 |  | 0
W | Seamless polyurethane (PU) resin screed / PU coating to parking decks & ramps |  | 1814.2 | - | m2 |  | 0 | ADDED - shown on tiling legend
X | Ceramic/porcelain wall tiles to washrooms, adhesive & grout (type TBC) |  | 2276.8816 | - | m2 |  | 0 | ADDED - wall tiling to washrooms
Doors
525mm Solid Panel door consisting of 100mm stiles,
| top and intermediate rail 225mm | [5 empty] | .
A | Ditto 1800mm X 2400mm Glazed entrance door assembly security door [PER DRAWINGS: 2-hour fire-rated double-leaf galvanised steel door (D1) - not glazed entrance door] | 1 | 1 | nr | nr |  | 0
B | Ditto 1000mm X 2200mm (D3) [PER DRAWINGS: D2: 1-hour fire-rated galvanised steel single-leaf security door - not D3] | 59 | 59 | nr | nr |  | 0
C | 900mm X 2200mm single leaf timber panel door | 126 | 126 | nr | nr |  | 0
D | Ditto 900mm X 2350mm flush door with fanlight [PER DRAWINGS: D4 is a single leaf timber PANEL door with fanlight] | 1 | 1 | nr | nr |  | 0
E | Ditto 3200mm X 2200mm flush door 4 Panel Galvanized steel framed tempered glass sliding door assembly [PER DRAWINGS: D5: 4-panel galvanised steel framed tempered glass sliding door (not flush)] | 1 | 1 | nr | nr |  | 0
F | Ditto 750mm X 2200mm flush door [PER DRAWINGS: D6: single leaf timber flush door] | 172 | 172 | nr | nr |  | 0
G | 50mm X 150mm Frames | 459 | 1600.5 | m | m |  | 0 | BOQ =9*51 (459 m) - frames to timber doors measured from schedule
H | 50mm x12mm Door stop | 459 | 1600.5 | m | m |  | 0
J | Single door 700 x 2200 security door single leaf [PER DRAWINGS: D7: single-leaf 2-hour fire-rated galvanised steel door] | 12 | 12 | nr | nr |  | 0
K | Single door 1200 x 2200 security door single leaf [PER DRAWINGS: D8: 1-hour fire-rated leaf-and-a-half galvanised steel security door] | 21 | 21 | nr | nr |  | 0
L | Single door 1000 x 2200 security door one and half [PER DRAWINGS: ED1: 1-hour fire-rated galvanised steel SINGLE-leaf security door (emergency stairs)] | 36 | 36 | nr | nr |  | 0
M | Single door 1000 x 2200 security door single leaf translucent glass panel | 20 | 20 | nr | nr |  | 0
N | 900mm X 2200 security door galvanised steel | 13 | 13 | nr | nr |  | 0
P | 1800mm X 2200mm double leaf galvanized steel [PER DRAWINGS: MD1: double-leaf 2-hour fire-rated galvanised steel refuse room door] | 3 | 3 | nr | nr |  | 0
Q | 1500mm X 2200mm Timber Bi-Fold Door | 7 | 7 | nr | nr |  | 0
R | 900mm X 2200mm Screw fixed galvanized steel service access panel | 18 | 18 | nr | nr |  | 0
S | 750mm X 2200mm Screw fixed galvanized steel service | 36 | 36 | nr | nr |  | 0
T | 450mm X 2200mm Screw fixed galvanized steel service | 8 | 8 | nr | nr |  | 0
U | 600mm X 2200mm Screw fixed galvanized steel service | 24 | 24 | nr | nr |  | 0
V | 1800mm X 2200mm Double leaf Double swing galvanixed steel framed tempered glass Door | 2 | 2 | nr | nr |  | 0
W | 2400mm X 2200mm Double leaf Double swing galvanixed steel framed tempered glass Door | 2 | 2 | nr | nr |  | 0
X | 5050mm X 2200mm Double leaf Double swing galvanixed steel framed tempered glass Door [PER DRAWINGS: DW2: 1 nr only, with fanlight and fixed side windows] | 2 | 1 | nr | nr |  | 0
Y | 3000mm X 2200 3 panel galvanised steel framed tempered glass sliding door | 8 | 8 | nr | nr |  | 0
Z | 1600mm X 2200mm 2 panel galvanized steel framed tempered glass sliding door | 28 | 28 | nr | nr |  | 0
A | 1300mm X 2200mm 2 panel galvanized steel framed tempered glass sliding door | 16 | 16 | nr | nr |  | 0
B | 1800mm X 2200mm 2 panel galvanized steel framed tempered glass sliding door | 30 | 30 | nr | nr |  | 0
C | 1200mm X 2200mm 2 panel galvanized steel framed tempered glass sliding door | 7 | 7 | nr | nr |  | 0
D | Metal roller shutter door 4200mm X 2157mm | 2 | 2 | nr | nr |  | 0
Ironmongery
Supply and fix the following approved Ironmongery
to hardwood with accommpanying pattented screws
A | Pair 100mm Brass butt hinges | 670 | 449 | nr | pr |  | 0 | Unit changed nr -> pairs
B | Ordinary locks | 558 | 127 | nr | nr |  | 0 | Steel security/fire doors carry own lock sets
C | Approved high quality mortice indicator lock . | 558 | 172 | nr | nr |  | 0
BURGLAR-PROOFING
Allow a Sum of GH₵ …....... for metal collaspble
burglar-proofing to internal windows including painting
D | fixed to ground floor windows |  |  | item | item |  |  | Provisional sum - measured as item (no quantity)
| TO COLLECTION | [5 empty] | 0
Item | Description | Qty | Verified Qty | Unit | Verified Unit | Rate | Amount | Verification remarks
GLAZING
ALUMINIUM GLAZED WINDOW
Supply and installation of Italian Extruded Aluminium Glazed windows
The Windows and Door share be ALCOA R50
series and produced in powder coated aluminium
profile, glazed with 6mm tinted reflective
glass secured onto galvanized steel sub frames
and complete with all accessories as per .
Architect's detail
A | 4 x 2 bay alu. Framed glass awning window 3600mm x 1900mm | 1 | 1 | nr | nr |  | 0
B | 2 bay alu. Framed glass sliding window 1800mm x 1300mm | 44 | 44 | nr | nr |  | 0
C | 2 bay alu. Framed glass sliding window 1800mm x 1500mm | 1 | 1 | nr | nr |  | 0
D | 1 bay alu. Framed glass awning window 900mm x 1300mm | 77 | 77 | nr | nr |  | 0
E | 2 bay alu. Framed glass sliding window 1800mm x 1900mm | 1 | 1 | nr | nr |  | 0
F | L shaped alu. Framed fixed glass 1750mm x 1750mm x 1500mm | 1 | 1 | nr | nr |  | 0
G | 2 bay alu. Framed glass sliding window 1800mm x 1600mm | 12 | 12 | nr | nr |  | 0
H | 1 x 3 bay alu. Framed glass awning window 1200mm x 1900 | 22 | 22 | nr | nr |  | 0
J | 2 bay alu. Framed glass sliding window 1200mm x 1150mm | 61 | 61 | nr | nr |  | 0
K | 2 bay alu. Framed glass sliding window 1200mm x 1200mm | 8 | 8 | nr | nr |  | 0
L | 2 bay alu. Framed glass sliding window 1500mm x 1300mm | 47 | 47 | nr | nr |  | 0
M | 2 bay alu. Framed glass sliding window 1500mm x 1150mm | 27 | 27 | nr | nr |  | 0
N | 3 bay alu. Framed glass wning window 2400mm x 1300mm | 6 | 6 | nr | nr |  | 0
P | 3 bay alu. Framed glass wning window 3600mm x 2200mm [PER DRAWINGS: W14 is a 3-bay SLIDING window 3600x2200] | 3 | 3 | nr | nr |  | 0
Q | 3 bay alu. Framed glass wning window 3000mm x 1600mm [PER DRAWINGS: W15 is a 3-bay SLIDING window 3000x1600] | 8 | 8 | nr | nr |  | 0
R | 2 x 3 alu. Framed glass awning window 240mm x 1900mm [PER DRAWINGS: W16: 3x2 awning window 2400 x 1900 (not 240)] | 2 | 2 | nr | nr |  | 0
S | 2 x 3 alu. Framed glass awning window 1800mm x 1900mm | 22 | 22 | nr | nr |  | 0
T | 1 bay alu. Framed glass awning window 750mm x 1300mm | 7 | 7 | nr | nr |  | 0
U | 3 bay alu. Framed glass sliding window 2100mm x 900mm | 2 | 2 | nr | nr |  | 0
V | 2 x 3 alu. Framed glass awning window 1450mm x 1900mm | 6 | 6 | nr | nr |  | 0
W | 2 bay alu. Framed glass sliding window 900mm x 600mm | 104 | 104 | nr | nr |  | 0
X | 2 bay alu. Framed glass sliding window 750mm x 600mm | 40 | 40 | nr | nr |  | 0
Y | 2 bay alu. Framed glass sliding window 600mm x 600mm | 12 | 12 | nr | nr |  | 0
Z | 2 bay alu. Framed glass sliding window 1200mm x 600mm | 12 | 12 | nr | nr |  | 0
WATERPROOFING
A | Liquid/applied waterproofing to roofs, terraces and wet external areas | 2200 | 942.1 | m² | m² |  | 0 | BOQ 2,200 m2 not supported by drawings
B | Protective cement-sand screed over waterproofing | 2200 | 942.1 | m² | m² |  | 0
C | Metal/aluminium flashings, upstands and counterflashings | 850 | 304.8 | m | m |  | 0
D | Roof/terrace gutters and concealed drainage channels | 480 | 304.8 | m | m |  | 0
LIFTS
E | 1000kg stainless steel car finish of lift with 12 passengers | 2 | 2 | nr | nr |  | 0
F | Service and goods lift | 1 | 0 | nr | nr |  | 0 | RFI - not shown on drawings
JOINERY & FITTING
G | Provide provisional sum of GHC….... for joinery, wall cladding, balustrade and other fitting works |  |  |  | item |  |  | Provisional sum - measured as item (no quantity)
FURNITURE AND EQUIPMENT
H | Provide provisional sum of GHC ….... for furniture and equipment (Wardbrobes, kitchen cabinets, receiption desk and chair) |  |  |  | item |  |  | Provisional sum - measured as item (no quantity)
EXTERNAL WORKS /EXTERNAL INFRASTRUCTURE /SIGNAGE
J | Provide provisional sum of GHC…... for axonopus compressus kerbs boundary structures and aprons, street lights, flood lights, storm drains, pavement, pavement markings, lanscaping, signs and other works |  |  |  | item |  |  | Provisional sum - measured as item (no quantity)
SCEPTIC TANK
K | Provide provisional sum of GHC…... for sceptic tank and other connections |  |  |  | item |  |  | Provisional sum - measured as item (no quantity)
| SUMMARY | [5 empty] | 0
Item | Description | Qty | Verified Qty | Unit | Verified Unit | Rate | Amount | Verification remarks
GENERAL SUMMARY
A | SUPERSTRUCTURE | [5 empty] | 0
| TOTAL | [5 empty] | 0

## general summary
Item | Description | Qty | Unit | Rate | Amount
GENERAL SUMMARY
A | PRELIMINARIES |  |  |  | 0
B | STRUCTURAL |  |  |  | 0 | 0
C | ARCHITECTURAL |  |  |  | 0
| SUB TOTAL |  |  |  | 0
| CONTIGENCY (10%) |  |  |  | 0
| TOTAL |  |  |  | 0

## Verification Take-off
VERIFICATION TAKE-OFF - PROPOSED KANESHIE BLOCK N REDEVELOPMENT
Every verified quantity in the BOQ links to the Result column of this sheet. Calculations are shown as formulas (dimensions in metres unless noted). Blue = dimensions taken from drawings.
Ref | BOQ sheet / item | Description | Calculation (dimensions) | Result | Unit | Source / basis
A. SUBSTRUCTURE - EARTHWORKS (STR-001 raft GA & Section A-A; ARCH-101/102 site & block plan)
S1 | STR A | Site clearance: Block N plot + Parking-22 forecourt | '=40.85*38.27+35.2*20.9 | 2299.0095 | m2 | ARCH-102 block plan: plot 3945+36900 wide x 38272 deep; Parking-22 5549+28051+1619 x (4900+5000+6000+5000)
S2 | STR B | Strip topsoil 150mm over excavation footprint (raft 41.0 x 36.0 + 2.0m working space each side) | '=(41.0+2*2.0)*(36.0+2*2.0) | 1800 | m2 | STR-001 Section A-A: raft width 41,000; width of excavation 45,000 (2,000 allowance each side). Raft depth 36.0 m measured on STR-001 at 1:100
S3 | STR C | Excavate to reduce levels, max depth 4.00m | '=(45.0*40.0)*4.0 | 7200 | m3 | STR-001: bottom of excavation -4,000mm
S4 | STR D | Fill to make up levels over raft to underside of hardcore (raft top -1.000 to -0.000) | '=41.0*36.0*1.0-(69.445*0.25*1.0)-(13.294*1.0) | 1445.3447 | m3 | Raft top SSL -1.000 (STR-007/017), GF +0.300 less 150 bed & 150 hardcore; core walls (69.445m x 0.25) and columns (13.294 m2 plan) deducted
S5 | STR E | Crushed rock / geogrid layers between raft underside (-2.300) and formation (-4.000), full excavation width | '=(45.0*40.0)*1.7 | 3060 | m3 | STR-001 Section A-A layer build-up. NB section dims show 2,700 below raft; levels give 1,700 - RFI
S6 | STR F | Backfill around raft in working space (outside raft, above crushed-rock layer) | '=((45.0*40.0)-(41.0*36.0))*(4.0-1.7) | 745.2 | m3 | Working-space area x depth from NGL to top of crushed rock
S7 | STR G | Disposal of surplus excavated material | '=(45.0*40.0)*4.0-((45.0*40.0)-(41.0*36.0))*(4.0-1.7) | 6454.8 | m3 | Excavation less re-used backfill (fills D/E/H are imported)
S8 | STR H | Hardcore 150mm under GF bed | '=41.0*36.0*0.15 | 221.4 | m3 | GF bed footprint taken as raft footprint
S9 | STR J | Blinding under raft - 100mm min. (General Notes 1.0 item 3) | '=41.0*36.0*0.10 | 147.6 | m3 | STR-000: "minimum 100mm thick blinding" - BOQ describes 50mm
S10 | STR K | 150mm thick bed (GF slab on fill) | '=41.0*36.0*0.15 | 221.4 | m3 | No GF slab detail on structural drawings - RFI
B. SUBSTRUCTURE - CONCRETE, REINFORCEMENT, FORMWORK, BLOCKWORK
S11 | STR A (p2) | Concrete walls from raft top (-1.000) to GF (+0.300): main core shear 22.05m + lift 21.825m + emergency core 25.57m, 250 thk | '=(22.05+21.825+25.57)*0.25*1.3 | 22.5696 | m3 | Wall lengths from raft GA STR-002 dims; walls 250 thk
S12 | STR B (p2) | Raft 1300 thick | '=41.0*36.0*1.3 | 1918.8 | m3 | Sump/lift-pit transitions (STR-003) not adjusted - same thickness folded
S13 | STR C (p2) | Columns raft to GF: 9 nr type-01 (750x500) + 25 nr type-02 (1200x300) + SWC-01A L-shape | '=(9*0.75*0.5+25*1.2*0.3+(2.85*0.25+(1.075-0.25)*0.25))*1.3 | 17.2819 | m3 | STR-007..012 sections; counts STR-002
S14 | STR D (p2) | Y20 in raft | '=2.466 | 2.466 | t | Reinforcement take-off (raft BBS STR-004..006)
S15 | STR E (p2) | Y25 in raft | '=184.672 | 184.672 | t | Reinforcement take-off (raft BBS)
S16 | STR F (p2) | Y10 links - columns & walls (substructure) | '=3.252+0.26+0.517 | 4.029 | t | Columns + lift walls + shear walls, Foundation-GF storey
S17 | STR G (p2) | Y12 - walls (substructure) | '=0.39+0.863 | 1.253 | t | Wall horizontal bars
S18 | STR H (p2) | Y25 - columns & walls (substructure starters) | '=6.531+4.935+9.84 | 21.306 | t | Column & wall vertical starters
S19 | STR NEW | Y20 - columns (substructure, SWC/type-02 starters) | '=0.338 | 0.338 | t | Not in BOQ
S20 | STR (p2) Walls fwk | Formwork to concrete walls (substructure), both faces | '=2*(22.05+21.825+25.57)*1.3 | 180.557 | m2
S21 | STR J (p2) | Edges of GF bed 150mm high (perimeter) | '=2*(41.0+36.0) | 154 | m | Edge <=250 high - measured linear (m), not m2
S22 | STR NEW | Formwork to edges of raft 1300 high | '=2*(41.0+36.0)*1.3 | 200.2 | m2 | Not in BOQ
S23 | STR NEW | Formwork to columns raft to GF | '=(9*2*(0.75+0.5)+25*2*(1.2+0.3)+2*(2.85+1.075))*1.3 | 136.955 | m2 | Not in BOQ
S24 | STR K (p2) | 150mm blockwork to plinth (GF perimeter, -1.000 to +0.300) | '=2*(41.0+36.0)*1.3 | 200.2 | m2 | Perimeter of raft x plinth height
C. SUPERSTRUCTURE - CONCRETE (C40)
C1 | STR A (sup) | Lintels 150x225 over all door & window openings (opening width + 150 bearing each end) | '=(1*(1.8+0.3)+59*(1+0.3)+126*(0.9+0.3)+1*(0.9+0.3)+1*(3.2+0.3)+172*(0.75+0.3)+12*(0.7+0.3)+21*(1.2+0.3)+36*(1+0.3)+20*(1+0.3)+13*(0.9+0.3)+3*(1.8+0.3)+7*(1.5+0.3)+18*(0.9+0.3)+36*(0.75+0.3)+8*(0.45+0.3)+24*(0.6+0.3)+2*(1.8+0.3)+2*(2.4+0.3)+1*(5.05+0.3)+8*(3+0.3)+28*(1.6+0.3)+16*(1.3+0.3)+30*(1.8+0.3)+7*(1.2+0.3)+2*(4.2+0.3)+1*(3.6+0.3)+44*(1.8+0.3)+1*(1.8+0.3)+77*(0.9+0.3)+1*(1.8+0.3)+1*(3.5+0.3)+12*(1.8+0.3)+22*(1.2+0.3)+61*(1.2+0.3)+8*(1.2+0.3)+47*(1.5+0.3)+27*(1.5+0.3)+6*(2.4+0.3)+3*(3.6+0.3)+8*(3+0.3)+2*(2.4+0.3)+22*(1.8+0.3)+7*(0.75+0.3)+2*(2.1+0.3)+6*(1.45+0.3)+104*(0.9+0.3)+40*(0.75+0.3)+12*(0.6+0.3)+12*(1.2+0.3))*0.15*0.225 | 56.4131 | m3 | Door schedule ARCH-501, window schedule ARCH-502
C2 | STR B (sup) | Columns GF to top: nos x section area x sum of clear storey heights (storey - 0.25 slab) | '=5*0.75*0.5*28.15+1*0.75*0.5*34.25+2*0.75*0.5*37.15+1*0.75*0.5*34+3*1.2*0.3*28.15+6*1.2*0.3*34.25+1*1.2*0.3*37.15+15*1.2*0.3*34+1*(2.85*0.25+0.825*0.25)*28.15 | 433.4563 | m3 | Clear heights per column type from elevations STR-007..012: COL-01A 5 nr 28.15m; COL-01B 1 nr 34.25m; COL-01C 2 nr 37.15m; COL-01D 1 nr 34.00m; COL-02A 3 nr 28.15m; COL-02B 6 nr 34.25m; COL-02C 1 nr 37.15m; COL-02D 15 nr 34.00m; SWC-01A 1 nr 28.15m
C3 | STR C (sup) | Concrete walls GF-roof: main stair core 22.05m x 37.15m clear; lift walls 21.825m x 41.20m; emergency core 25.57m x 37.20m; 250 thk | '=(22.05*37.15+21.825*41.2+25.57*37.2)*0.25 | 667.3879 | m3 | Clear heights = sum(storey heights) - 0.25 per slab (STR-014/016/017 elevations)
C4 | STR D (sup) | Stairs: per storey 2 flights (waist 175, 1800 wide, 3.0m going) + 2 landings; scaled to storey height. Main 10 storeys (sum H 37.0m), emergency 12 storeys (sum H 37.3m) | '=2.966*(37.0+37.3)/3.3+2.625*(10+12) | 124.5299 | m3 | STR-018..039 GA: waist 175, treads 300, risers 150-160; per 3.3m storey: flights 2.966 m3, landings 2.625 m3
C5 | STR E (sup) | Suspended slabs 250 thk (areas measured from GA sheets, voids/stair & lift openings excluded) + roof 150 thk (176.3 m2) + lift-core top 150 thk (16.3 m2) | '=(689.1+737.6+650.6+737.5+554.9+1273.9+1134.6*5+1134.4+868.4+868.1)*0.25+(176.3+16.3)*0.15 | 3325.765 | m3 | Slab areas measured on STR-040/046/052/058/064/070/076/083/091/097/104/107 (scale calibrated on gridlines 1-12 = 36,500)
C6 | STR F (sup) | Copings 300x150 to parapets: roof terrace perimeter 182.5 + roof 105.0 + lift core 17.3 | '=(182.5+105.0+17.3)*0.3*0.15 | 13.716 | m3 | Slab outer perimeters measured on GA sheets
C7 | STR NEW | Beams (downstands below 250 slab): 300x600 = (67.8+81.1+63.6+79.9+64.3+97.4+166.8*5+186.5+122.2+125.7) m; 200x600 = (43.5+43.0+33.1+33.1*5+33.1+14.2+14.2) m; roof 250x600 31.4m & 200x450 34.0m below 150 slab | '=(67.8+81.1+63.6+79.9+64.3+97.4+166.8*5+186.5+122.2+125.7)*0.3*0.35+(43.5+43.0+33.1+33.1*5+33.1+14.2+14.2)*0.2*0.35+31.4*0.25*0.45+34.0*0.2*0.3 | 210.697 | m3 | Beam lengths measured from dashed beam outlines on GA sheets. NOT IN BOQ
D. SUPERSTRUCTURE - REINFORCEMENT (from Reinforcement Take-off workbook)
R1 | STR G (sup) | Y10 in columns | '=48.472 | 48.472 | t
R2 | STR H (sup) | Y20 in columns | '=56.589 | 56.589 | t
R3 | STR J (sup) | Y25 in columns | '=29.946 | 29.946 | t
R4 | STR K (sup) | Y12 in stairs (BOQ says 10mm - stairs use Y12 & Y16) | '=10.116 | 10.116 | t | Stair BBS STR-019..039
R5 | STR L (sup) | Y16 in stairs | '=16.226 | 16.226 | t
R6 | STR M (sup) | Y10 in shear & lift walls (links) | '=17.642+8.551 | 26.193 | t
R7 | STR N (sup) | Y12 in shear, lift & ramp walls | '=24.018+11.469+0.84 | 36.327 | t
R8 | STR P (sup) | Y25 in shear & lift walls | '=48.924+28.093 | 77.017 | t
R9 | STR Q (sup) | Y12 in suspended slabs (incl. lift core slab) | '=585.901+0.366 | 586.267 | t
R10 | STR R (sup) | Y16 in suspended slabs | '=11.42 | 11.42 | t
R11 | STR NEW | Y20 in shear & lift walls | '=54.981+27.171 | 82.152 | t | NOT IN BOQ
R12 | STR NEW | Y10 in beams | '=19.686 | 19.686 | t | NOT IN BOQ - beam BBS per floor
R13 | STR NEW | Y16 in beams | '=14.785 | 14.785 | t | NOT IN BOQ - beam BBS per floor
R14 | STR NEW | Y20 in beams | '=22.563 | 22.563 | t | NOT IN BOQ - beam BBS per floor
R15 | STR NEW | Y25 in beams | '=54.392 | 54.392 | t | NOT IN BOQ - beam BBS per floor
E. SUPERSTRUCTURE - FORMWORK
F1 | STR S (sup) | Lintels: sides 2x0.225 + soffit 0.15 per m; copings: sides 2x0.15 per m | '=(1*(1.8+0.3)+59*(1+0.3)+126*(0.9+0.3)+1*(0.9+0.3)+1*(3.2+0.3)+172*(0.75+0.3)+12*(0.7+0.3)+21*(1.2+0.3)+36*(1+0.3)+20*(1+0.3)+13*(0.9+0.3)+3*(1.8+0.3)+7*(1.5+0.3)+18*(0.9+0.3)+36*(0.75+0.3)+8*(0.45+0.3)+24*(0.6+0.3)+2*(1.8+0.3)+2*(2.4+0.3)+1*(5.05+0.3)+8*(3+0.3)+28*(1.6+0.3)+16*(1.3+0.3)+30*(1.8+0.3)+7*(1.2+0.3)+2*(4.2+0.3)+1*(3.6+0.3)+44*(1.8+0.3)+1*(1.8+0.3)+77*(0.9+0.3)+1*(1.8+0.3)+1*(3.5+0.3)+12*(1.8+0.3)+22*(1.2+0.3)+61*(1.2+0.3)+8*(1.2+0.3)+47*(1.5+0.3)+27*(1.5+0.3)+6*(2.4+0.3)+3*(3.6+0.3)+8*(3+0.3)+2*(2.4+0.3)+22*(1.8+0.3)+7*(0.75+0.3)+2*(2.1+0.3)+6*(1.45+0.3)+104*(0.9+0.3)+40*(0.75+0.3)+12*(0.6+0.3)+12*(1.2+0.3))*(2*0.225+0.15)+(182.5+105.0+17.3)*2*0.15 | 1094.34 | m2
F2 | STR T (sup) | Columns: nos x perimeter x clear height | '=5*2*(0.75+0.5)*28.15+1*2*(0.75+0.5)*34.25+2*2*(0.75+0.5)*37.15+1*2*(0.75+0.5)*34+3*2*(1.2+0.3)*28.15+6*2*(1.2+0.3)*34.25+1*2*(1.2+0.3)*37.15+15*2*(1.2+0.3)*34+1*2*(2.85+1.075)*28.15 | 3440.5275 | m2
F3 | STR U (sup) | Soffits of suspended slabs (same areas as concrete) | '=(689.1+737.6+650.6+737.5+554.9+1273.9+1134.6*5+1134.4+868.4+868.1)+(176.3+16.3) | 13380.1 | m2
F4 | STR V (sup) | Concrete walls, both faces | '=2*(22.05*37.15+21.825*41.2+25.57*37.2) | 5339.103 | m2 | BOQ formula =C98/0.25 refers to the columns line - error
F5 | STR NEW | Beams: sides of downstand + soffit | '=(67.8+81.1+63.6+79.9+64.3+97.4+166.8*5+186.5+122.2+125.7)*(2*0.35+0.3)+(43.5+43.0+33.1+33.1*5+33.1+14.2+14.2)*(2*0.35+0.2)+31.4*(2*0.45+0.25)+34.0*(2*0.3+0.2) | 2097.75 | m2 | NOT IN BOQ
F6 | STR NEW | Edges of suspended slabs 250 high (outer + void edges) | '=238.4+185.9+224.9+186.5+216.4+232.4+294.6*5+294.5+252.6+252.9+159.3+17.3 | 3734.1 | m | Perimeters measured on GA sheets. NOT IN BOQ
F7 | STR NEW | Stair soffits & risers (per storey 33.3 m2 x 22 storey-flights) | '=(2*3.424*1.8+15.0+22*0.15*1.8)*22 | 731.8608 | m2 | NOT IN BOQ
F. ARCHITECTURAL - BLOCKWORK & WALL FINISHES (walls measured on ARCH-103..125 plans at 1:100; openings already excluded from lengths)
A0a | ARCH calc | 150 walls: sum(length x clear height) per floor | '=203.6*3.6+98.4*2.45+144.5*2.45+127.5*2.45+500.0*3.05+443.9*3.05+447.7*3.05+465.9*3.05+449.8*3.05+441.2*3.05+397.2*3.05+354.0*3.05+82.0*2.9+6.5*1.2 | 12560.125 | m2 | Lengths per floor: GF 204m; 1F 98m; 2F 145m; MEZZ 128m; 3F 500m; 4F 444m; 5F 448m; 6F 466m; 7F 450m; 8F 441m; 9F 397m; 10F 354m; RT 82m; ROOF 7m
A0b | ARCH calc | 200 walls: sum(length x clear height) per floor | '=33.8*3.6+36.6*2.45+16.7*2.45+31.6*2.45+47.2*3.05+55.3*3.05+49.2*3.05+50.0*3.05+50.1*3.05+51.7*3.05+25.6*3.05+31.1*3.05+10.2*2.9+65.7*1.2 | 1536.715 | m2 | Lengths per floor: GF 34m; 1F 37m; 2F 17m; MEZZ 32m; 3F 47m; 4F 55m; 5F 49m; 6F 50m; 7F 50m; 8F 52m; 9F 26m; 10F 31m; RT 10m; ROOF 66m
A0c | ARCH calc | Add back walling above/below openings (avg clear height 3.05m) | '=1*1.8*(3.05-2.4)+59*1*(3.05-2.2)+126*0.9*(3.05-2.2)+1*0.9*(3.05-2.35)+1*3.2*(3.05-2.2)+172*0.75*(3.05-2.2)+12*0.7*(3.05-2.2)+21*1.2*(3.05-2.2)+36*1*(3.05-2.2)+20*1*(3.05-2.2)+13*0.9*(3.05-2.2)+3*1.8*(3.05-2.2)+7*1.5*(3.05-2.2)+18*0.9*(3.05-2.2)+36*0.75*(3.05-2.2)+8*0.45*(3.05-2.2)+24*0.6*(3.05-2.2)+2*1.8*(3.05-2.2)+2*2.4*(3.05-2.2)+1*5.05*(3.05-2.2)+8*3*(3.05-2.2)+28*1.6*(3.05-2.2)+16*1.3*(3.05-2.2)+30*1.8*(3.05-2.2)+7*1.2*(3.05-2.2)+2*4.2*(3.05-2.157)+1*3.6*(3.05-1.9)+44*1.8*(3.05-1.3)+1*1.8*(3.05-1.5)+77*0.9*(3.05-1.3)+1*1.8*(3.05-1.9)+1*3.5*(3.05-1.5)+12*1.8*(3.05-1.6)+22*1.2*(3.05-1.9)+61*1.2*(3.05-1.15)+8*1.2*(3.05-1.2)+47*1.5*(3.05-1.3)+27*1.5*(3.05-1.15)+6*2.4*(3.05-1.3)+3*3.6*(3.05-2.2)+8*3*(3.05-1.6)+2*2.4*(3.05-1.9)+22*1.8*(3.05-1.9)+7*0.75*(3.05-1.3)+2*2.1*(3.05-0.9)+6*1.45*(3.05-1.9)+104*0.9*(3.05-0.6)+40*0.75*(3.05-0.6)+12*0.6*(3.05-0.6)+12*1.2*(3.05-0.6) | 1757.8312 | m2 | Door & window schedules
A1 | ARCH A | 150mm sandcrete blockwork | '=E64+E66*0.882 | 14110.5321 | m2 | Openings add-back apportioned by length (150 share 0.882)
A1b | ARCH NEW | 200mm sandcrete blockwork | '=E65+E66*0.118 | 1744.1391 | m2 | Wall band 200-225 thick on plans. NOT IN BOQ
A0d | ARCH calc | Total window area (schedule) | '=1*3.6*1.9+44*1.8*1.3+1*1.8*1.5+77*0.9*1.3+1*1.8*1.9+1*3.5*1.5+12*1.8*1.6+22*1.2*1.9+61*1.2*1.15+8*1.2*1.2+47*1.5*1.3+27*1.5*1.15+6*2.4*1.3+3*3.6*2.2+8*3*1.6+2*2.4*1.9+22*1.8*1.9+7*0.75*1.3+2*2.1*0.9+6*1.45*1.9+104*0.9*0.6+40*0.75*0.6+12*0.6*0.6+12*1.2*0.6 | 809.4 | m2
A0e | ARCH calc | Total door area (schedule) | '=1*1.8*2.4+59*1*2.2+126*0.9*2.2+1*0.9*2.35+1*3.2*2.2+172*0.75*2.2+12*0.7*2.2+21*1.2*2.2+36*1*2.2+20*1*2.2+13*0.9*2.2+3*1.8*2.2+7*1.5*2.2+18*0.9*2.2+36*0.75*2.2+8*0.45*2.2+24*0.6*2.2+2*1.8*2.2+2*2.4*2.2+1*5.05*2.2+8*3*2.2+28*1.6*2.2+16*1.3*2.2+30*1.8*2.2+7*1.2*2.2+2*4.2*2.157 | 1451.1438 | m2
A0f | ARCH calc | Internal wall faces: (2 x block length + 2 x RC core length - 16.8 lift-shaft faces - external wall length) x clear height, per floor | '=(2*(203.6+33.8)+2*41.6-16.8-142.2)*3.6+(2*(98.4+36.6)+2*25.8-16.8-134.3)*2.45+(2*(144.5+16.7)+2*35.1-16.8-134.0)*2.45+(2*(127.5+31.6)+2*42.8-16.8-191.5)*2.45+(2*(500.0+47.2)+2*49.4-16.8-148.0)*3.05+(2*(443.9+55.3)+2*46.5-16.8-224.2)*3.05+(2*(447.7+49.2)+2*67.8-16.8-224.2)*3.05+(2*(465.9+50.0)+2*64.6-16.8-224.2)*3.05+(2*(449.8+50.1)+2*67.4-16.8-224.2)*3.05+(2*(441.2+51.7)+2*67.3-16.8-224.2)*3.05+(2*(397.2+25.6)+2*51.7-16.8-224.1)*3.05+(2*(354.0+31.1)+2*39.8-16.8-181.8)*3.05+(2*(82.0+10.2)+2*42.3-16.8-182.5)*2.9 | 23927.115 | m2 | External wall length = measured slab outer perimeter per floor
A0g | ARCH calc | Washroom wall faces: nr washrooms (wet area/3.8 m2 each) x 8.0m perimeter x clear height | '=18.1/3.8*8.0*3.6+59.2/3.8*8.0*3.05+62.1/3.8*8.0*3.05+56.0/3.8*8.0*3.05+61.4/3.8*8.0*3.05+57.5/3.8*8.0*3.05+60.4/3.8*8.0*3.05+48.7/3.8*8.0*3.05+45.4/3.8*8.0*3.05+24.2/3.8*8.0*2.9 | 3178.8947 | m2 | Wet areas per floor from tiling layouts: GF 18; 3F 59; 4F 62; 5F 56; 6F 61; 7F 57; 8F 60; 9F 49; 10F 45; RT 24
A2 | ARCH B | Render to interior walls (excl. washrooms) | '=E71-E72-2*E70-E69 | 17036.5327 | m2 | Internal faces less washroom walls, doors (2 faces) and windows (1 face)
A3 | ARCH C | Render to washroom walls | '=E72-129.7*0.75*2.2 | 2964.8897 | m2 | Less washroom doors 750x2200
A4 | ARCH NEW | External render (12.5mm cement-sand) to external walls | '=142.2*3.85+134.3*2.7+134.0*2.7+191.5*2.7+148.0*3.3+224.2*3.3+224.2*3.3+224.2*3.3+224.2*3.3+224.2*3.3+224.1*3.3+181.8*3.3+182.5*3.15-E69 | 7081.575 | m2 | NOT IN BOQ: external wall length x storey height less windows
G. ARCHITECTURAL - FLOOR FINISHES (tile types per legend ARCH-401..409; rooms measured on plans and classified by room label / hatch)
T1 | ARCH Q | 40x40 non-slip porcelain - washrooms/WCs | '=493.0 | 493 | m2 | Per floor: GF 18.1; 3F 59.2; 4F 62.1; 5F 56.0; 6F 61.4; 7F 57.5; 8F 60.4; 9F 48.7; 10F 45.4; RT 24.2
T2 | ARCH R | 50x50 matte R11 porcelain - staircases (treads, risers, landings): 22 storey-flights x 31.74 m2 | '=(2*1.8*3.0+22*0.15*1.8+2.2*3.75+1.8*3.75)*22 | 698.28 | m2 | Legend: 50x50 R11 used on stair cores
T3 | ARCH S | 60x60 semi-polished porcelain - habitable rooms, shops, offices | '=4573.9 | 4573.9 | m2 | Incl. GF Shop 2 86.2 m2 added manually
T4 | ARCH T | 60x120 semi-polished porcelain - FLOOR to stair/lift lobbies & reception | '=357.4 | 357.4 | m2 | Legend shows 60x120 as floor tile in lobbies (BOQ says wall)
T5 | ARCH U | 60x60 non-slip R11 - corridors, terraces, verandah, service rooms | '=2219.9 | 2219.9 | m2 | RT outdoor sitting (412.1) and Mezz parking (176.8) re-allocated; GF verandah 47.0 added
T6 | ARCH V | Interlocking composite tiles - 9th floor play area & roof-top outdoor sitting | '=750.5 | 750.5 | m2 | ARCH-601..606 details
T7 | ARCH NEW | Seamless PU resin screed / PU coating to parking decks & ramps | '=1814.2 | 1814.2 | m2 | Legend items; NOT IN BOQ
T8 | ARCH calc | Total tiled floor area (excl. stairs, interlocking, PU) | '=493.0+4573.9+357.4+2219.9 | 7644.2 | m2
A5 | ARCH D | 25mm cement-sand screed to tiled floors | '=E84 | 7644.2 | m2 | BOQ 17,600 appears to be gross slab area
A6 | ARCH P | 12mm bed to receive floor tiles (floors + stairs) | '=E84+(2*1.8*3.0+22*0.15*1.8+2.2*3.75+1.8*3.75)*22 | 8342.48 | m2
A7 | ARCH N | 12mm backing to receive wall tiles - washroom walls to 2.4m high | '=493.0/3.8*8.0*2.4-493.0/3.8*0.75*2.2 | 2276.8816 | m2 | Wall tile height assumed 2.4m (not dimensioned on drawings)
A8 | ARCH NEW | Wall tiles to washrooms (type to be confirmed) | '=E87 | 2276.8816 | m2 | NOT IN BOQ as wall item (BOQ T is a floor tile per legend)
H. ARCHITECTURAL - PAINTING & CEILINGS
P1 | ARCH E | Emulsion paint to interior walls (same as render B) | '=E73 | 17036.5327 | m2
P2 | ARCH F | Emulsion to washroom walls above 2.4m tiling | '=E74-E87 | 688.0082 | m2
P3 | ARCH G | Emulsion/exterior paint to external walls | '=E75 | 7081.575 | m2
P4 | ARCH H | Paint to exposed faces of columns in GF & parking levels (girth exceeds 300mm) | '=5*2*(0.75+0.5)*9.85+1*2*(0.75+0.5)*9.85+2*2*(0.75+0.5)*9.85+1*2*(0.75+0.5)*9.60+3*2*(1.2+0.3)*9.85+6*2*(1.2+0.3)*9.85+1*2*(1.2+0.3)*9.85+15*2*(1.2+0.3)*9.60 | 948.5 | m2 | Columns GF to 3rd floor; all columns have girth > 300 mm so measured in m2
P5 | ARCH J | Plasterboard ceiling soffits - habitable rooms, corridors, lobbies (excl. parking) | '=4573.9+357.4+2219.9-22.2-20.0 | 7109 | m2 | Excludes 1st/Mezz parking-level tiled lobbies (est. 42 m2)
P6 | ARCH K | Plasterboard ceiling soffits - washrooms | '=493.0 | 493 | m2
P7 | ARCH L | Gloss paint to timber doors (D3, D4, D6, FD1 both faces) and frames (girth 0.25m) | '=126*0.9*2.2*2+1*0.9*2.35*2+172*0.75*2.2*2+7*1.5*2.2*2+(126*(2*2.2+0.9)+1*(2*2.35+0.9)+172*(2*2.2+0.75)+7*(2*2.2+1.5))*0.25 | 1517.115 | m2 | Door schedule ARCH-501
P8 | ARCH M | Primer/paint to burglar-proof bars over window openings | '=E69 | 809.4 | m2 | Measured as area of window openings (all windows) - confirm extent with client (BOQ item D says GF only)
I. DOORS, IRONMONGERY, WINDOWS (schedules ARCH-501/502)
J1 | ARCH G (doors) | 50x150 frames to timber doors (D3,D4,D6,FD1): 2 jambs + head | '=126*(2*2.2+0.9)+1*(2*2.35+0.9)+172*(2*2.2+0.75)+7*(2*2.2+1.5) | 1600.5 | m
J2 | ARCH H (doors) | 50x12 door stops (same as frames) | '=126*(2*2.2+0.9)+1*(2*2.35+0.9)+172*(2*2.2+0.75)+7*(2*2.2+1.5) | 1600.5 | m
J3 | ARCH A (ironm.) | Pairs 100mm brass butt hinges: 1.5 pairs per timber leaf (299 leaves) | '=ROUNDUP(1.5*(126+1+172),0) | 449 | pr | Steel doors are supplied as assemblies with hinges
J4 | ARCH B (ironm.) | Ordinary mortice locks - timber panel doors D3 & D4 | '=126+1 | 127 | nr
J5 | ARCH C (ironm.) | Mortice indicator (bathroom) locks - washroom flush doors D6 | '=172 | 172 | nr
J. WATERPROOFING & LIFTS
K1 | ARCH A (wp) | Liquid waterproofing: roof-top outdoor sitting 412.1 + 9th-floor play area 337.4 + roof slab 176.3 + lift-core top 16.3 | '=412.1+337.4+176.3+16.3 | 942.1 | m2 | Floor terraces within units excluded (covered) - confirm
K2 | ARCH B (wp) | Protective screed over waterproofing | '=412.1+337.4+176.3+16.3 | 942.1 | m2
K3 | ARCH C (wp) | Flashings/upstands at parapets: roof terrace 182.5 + roof 105.0 + lift core 17.3 | '=182.5+105.0+17.3 | 304.8 | m
K4 | ARCH D (wp) | Perimeter gutters/drainage channels (same perimeters) | '=182.5+105.0+17.3 | 304.8 | m | No roof drainage layout on drawings - RFI
K5 | ARCH E (lifts) | Passenger lifts (LIFT 1, LIFT 2 on plans) | '=2 | 2 | nr
K6 | ARCH F (lifts) | Service/goods lift | '=0 | 0 | nr | Not shown on any plan - only 2 lift shafts in core. RFI
DOOR87 | ARCH doors row 87 | Door per schedule ARCH-501: Ditto 1800mm X 2400mm Glazed entrance door assembly security door | '=1 | 1 | nr | Schedule quantity (doors are not tagged on plans)
DOOR89 | ARCH doors row 89 | Door per schedule ARCH-501: Ditto 1000mm X 2200mm (D3) | '=59 | 59 | nr | Schedule quantity (doors are not tagged on plans)
DOOR91 | ARCH doors row 91 | Door per schedule ARCH-501: 900mm X 2200mm single leaf timber panel door | '=126 | 126 | nr | Schedule quantity (doors are not tagged on plans)
DOOR93 | ARCH doors row 93 | Door per schedule ARCH-501: Ditto 900mm X 2350mm flush door with fanlight | '=1 | 1 | nr | Schedule quantity (doors are not tagged on plans)
DOOR95 | ARCH doors row 95 | Door per schedule ARCH-501: Ditto 3200mm X 2200mm flush door 4 Panel Galvanized steel framed tempered glass | '=1 | 1 | nr | Schedule quantity (doors are not tagged on plans)
DOOR97 | ARCH doors row 97 | Door per schedule ARCH-501: Ditto 750mm X 2200mm flush door | '=172 | 172 | nr | Schedule quantity (doors are not tagged on plans)
DOOR103 | ARCH doors row 103 | Door per schedule ARCH-501: Single door 700 x 2200 security door single leaf | '=12 | 12 | nr | Schedule quantity (doors are not tagged on plans)
DOOR105 | ARCH doors row 105 | Door per schedule ARCH-501: Single door 1200 x 2200 security door single leaf | '=21 | 21 | nr | Schedule quantity (doors are not tagged on plans)
DOOR107 | ARCH doors row 107 | Door per schedule ARCH-501: Single door 1000 x 2200 security door one and half | '=36 | 36 | nr | Schedule quantity (doors are not tagged on plans)
DOOR109 | ARCH doors row 109 | Door per schedule ARCH-501: Single door 1000 x 2200 security door single leaf translucent glass panel | '=20 | 20 | nr | Schedule quantity (doors are not tagged on plans)
DOOR111 | ARCH doors row 111 | Door per schedule ARCH-501: 900mm X 2200 security door galvanised steel | '=13 | 13 | nr | Schedule quantity (doors are not tagged on plans)
DOOR113 | ARCH doors row 113 | Door per schedule ARCH-501: 1800mm X 2200mm double leaf galvanized steel | '=3 | 3 | nr | Schedule quantity (doors are not tagged on plans)
DOOR115 | ARCH doors row 115 | Door per schedule ARCH-501: 1500mm X 2200mm Timber Bi-Fold Door | '=7 | 7 | nr | Schedule quantity (doors are not tagged on plans)
DOOR117 | ARCH doors row 117 | Door per schedule ARCH-501: 900mm X 2200mm Screw fixed galvanized steel service access panel | '=18 | 18 | nr | Schedule quantity (doors are not tagged on plans)
DOOR119 | ARCH doors row 119 | Door per schedule ARCH-501: 750mm X 2200mm Screw fixed galvanized steel service | '=36 | 36 | nr | Schedule quantity (doors are not tagged on plans)
DOOR121 | ARCH doors row 121 | Door per schedule ARCH-501: 450mm X 2200mm Screw fixed galvanized steel service | '=8 | 8 | nr | Schedule quantity (doors are not tagged on plans)
DOOR123 | ARCH doors row 123 | Door per schedule ARCH-501: 600mm X 2200mm Screw fixed galvanized steel service | '=24 | 24 | nr | Schedule quantity (doors are not tagged on plans)
DOOR125 | ARCH doors row 125 | Door per schedule ARCH-501: 1800mm X 2200mm Double leaf Double swing galvanixed steel framed tempered glass | '=2 | 2 | nr | Schedule quantity (doors are not tagged on plans)
DOOR127 | ARCH doors row 127 | Door per schedule ARCH-501: 2400mm X 2200mm Double leaf Double swing galvanixed steel framed tempered glass | '=2 | 2 | nr | Schedule quantity (doors are not tagged on plans)
DOOR129 | ARCH doors row 129 | Door per schedule ARCH-501: 5050mm X 2200mm Double leaf Double swing galvanixed steel framed tempered glass | '=1 | 1 | nr | Schedule quantity (doors are not tagged on plans)
DOOR131 | ARCH doors row 131 | Door per schedule ARCH-501: 3000mm X 2200 3 panel galvanised steel framed tempered glass sliding door | '=8 | 8 | nr | Schedule quantity (doors are not tagged on plans)
DOOR133 | ARCH doors row 133 | Door per schedule ARCH-501: 1600mm X 2200mm 2 panel galvanized steel framed tempered glass sliding door | '=28 | 28 | nr | Schedule quantity (doors are not tagged on plans)
DOOR135 | ARCH doors row 135 | Door per schedule ARCH-501: 1300mm X 2200mm 2 panel galvanized steel framed tempered glass sliding door | '=16 | 16 | nr | Schedule quantity (doors are not tagged on plans)
DOOR137 | ARCH doors row 137 | Door per schedule ARCH-501: 1800mm X 2200mm 2 panel galvanized steel framed tempered glass sliding door | '=30 | 30 | nr | Schedule quantity (doors are not tagged on plans)
DOOR139 | ARCH doors row 139 | Door per schedule ARCH-501: 1200mm X 2200mm 2 panel galvanized steel framed tempered glass sliding door | '=7 | 7 | nr | Schedule quantity (doors are not tagged on plans)
DOOR142 | ARCH doors row 142 | Door per schedule ARCH-501: Metal roller shutter door 4200mm X 2157mm | '=2 | 2 | nr | Schedule quantity (doors are not tagged on plans)
WIN184 | ARCH windows row 184 | Window per schedule ARCH-502: 4 x 2 bay alu. Framed glass awning window 3600mm x 1900mm | '=1 | 1 | nr | Schedule quantity
WIN186 | ARCH windows row 186 | Window per schedule ARCH-502: 2 bay alu. Framed glass sliding window 1800mm x 1300mm | '=44 | 44 | nr | Schedule quantity
WIN188 | ARCH windows row 188 | Window per schedule ARCH-502: 2 bay alu. Framed glass sliding window 1800mm x 1500mm | '=1 | 1 | nr | Schedule quantity
WIN190 | ARCH windows row 190 | Window per schedule ARCH-502: 1 bay alu. Framed glass awning window 900mm x 1300mm | '=77 | 77 | nr | Schedule quantity
WIN192 | ARCH windows row 192 | Window per schedule ARCH-502: 2 bay alu. Framed glass sliding window 1800mm x 1900mm | '=1 | 1 | nr | Schedule quantity
WIN194 | ARCH windows row 194 | Window per schedule ARCH-502: L shaped alu. Framed fixed glass 1750mm x 1750mm x 1500mm | '=1 | 1 | nr | Schedule quantity
WIN196 | ARCH windows row 196 | Window per schedule ARCH-502: 2 bay alu. Framed glass sliding window 1800mm x 1600mm | '=12 | 12 | nr | Schedule quantity
WIN198 | ARCH windows row 198 | Window per schedule ARCH-502: 1 x 3 bay alu. Framed glass awning window 1200mm x 1900 | '=22 | 22 | nr | Schedule quantity
WIN200 | ARCH windows row 200 | Window per schedule ARCH-502: 2 bay alu. Framed glass sliding window 1200mm x 1150mm | '=61 | 61 | nr | Schedule quantity
WIN202 | ARCH windows row 202 | Window per schedule ARCH-502: 2 bay alu. Framed glass sliding window 1200mm x 1200mm | '=8 | 8 | nr | Schedule quantity
WIN204 | ARCH windows row 204 | Window per schedule ARCH-502: 2 bay alu. Framed glass sliding window 1500mm x 1300mm | '=47 | 47 | nr | Schedule quantity
WIN206 | ARCH windows row 206 | Window per schedule ARCH-502: 2 bay alu. Framed glass sliding window 1500mm x 1150mm | '=27 | 27 | nr | Schedule quantity
WIN208 | ARCH windows row 208 | Window per schedule ARCH-502: 3 bay alu. Framed glass wning window 2400mm x 1300mm | '=6 | 6 | nr | Schedule quantity
WIN210 | ARCH windows row 210 | Window per schedule ARCH-502: 3 bay alu. Framed glass wning window 3600mm x 2200mm | '=3 | 3 | nr | Schedule quantity
WIN212 | ARCH windows row 212 | Window per schedule ARCH-502: 3 bay alu. Framed glass wning window 3000mm x 1600mm | '=8 | 8 | nr | Schedule quantity
WIN214 | ARCH windows row 214 | Window per schedule ARCH-502: 2 x 3 alu. Framed glass awning window 240mm x 1900mm | '=2 | 2 | nr | Schedule quantity
WIN216 | ARCH windows row 216 | Window per schedule ARCH-502: 2 x 3 alu. Framed glass awning window 1800mm x 1900mm | '=22 | 22 | nr | Schedule quantity
WIN218 | ARCH windows row 218 | Window per schedule ARCH-502: 1 bay alu. Framed glass awning window 750mm x 1300mm | '=7 | 7 | nr | Schedule quantity
WIN220 | ARCH windows row 220 | Window per schedule ARCH-502: 3 bay alu. Framed glass sliding window 2100mm x 900mm | '=2 | 2 | nr | Schedule quantity
WIN222 | ARCH windows row 222 | Window per schedule ARCH-502: 2 x 3 alu. Framed glass awning window 1450mm x 1900mm | '=6 | 6 | nr | Schedule quantity
WIN224 | ARCH windows row 224 | Window per schedule ARCH-502: 2 bay alu. Framed glass sliding window 900mm x 600mm | '=104 | 104 | nr | Schedule quantity
WIN226 | ARCH windows row 226 | Window per schedule ARCH-502: 2 bay alu. Framed glass sliding window 750mm x 600mm | '=40 | 40 | nr | Schedule quantity
WIN228 | ARCH windows row 228 | Window per schedule ARCH-502: 2 bay alu. Framed glass sliding window 600mm x 600mm | '=12 | 12 | nr | Schedule quantity
WIN230 | ARCH windows row 230 | Window per schedule ARCH-502: 2 bay alu. Framed glass sliding window 1200mm x 600mm | '=12 | 12 | nr | Schedule quantity